## resources
staff | capacity | team | contract
Dittmar, Andrew | 1 | B | INTERN
al-Radi, Nawwaara | 1 | C | INTERN
South, Marley | 1 | B | INTERN
Lee, Vinh | 1 | C | FTE
Mullens, Jonathan | 1 | B | INTERN
unassigned | 1

## projects
project | probability | launch
N | 1 | 2019-04-15
Y | 1 | 2019-04-28
H | 1 | 2019-05-29
Z | 1 | 2019-06-17
T | 0.5 | 2019-07-29
V | 1 | 2019-10-21
S | 1 | 2019-11-20
U | 1 | 2019-11-26
Q | 1 | 2019-12-24
L | 0.5 | 2019-12-24

## project.phases
phase | sequencing
research | 1
drafting | 2
editing | 3
design | 4
print | 5
launch-events | 6

## roles
role
lead
researcher
editor
design

## public.holidays
date | holiday.name | information
2019-01-01 | New Year's Day | New Year's Day is the first day of the calendar year and is celebrated each January 1st
2019-01-28 | Australia Day | Always celebrated on 26 January
2019-04-19 | Good Friday | Easter is celebrated with Good Friday and Easter Monday creating a 4 day long weekend.
2019-04-20 | Saturday before Easter Sunday | Easter Saturday is between Good Friday and Easter Sunday in Australia.
2019-04-21 | Easter Sunday | Public Holiday as part of Easter.
2019-04-22 | Easter Monday | Public Holiday as part of Easter.
2019-04-25 | Anzac Day | Celebrated on the 25 April each year.
2019-06-10 | Queen's Birthday | Celebrated on second Monday in June except in Western Australia and Queensland.
2019-08-05 | Bank Holiday | Applies to banks and certain financial institutions, per theÊRetail Trading Act 2008
2019-10-07 | Labour Day | Always on a Monday, creating a long weekend. It celebrates the eight-hour working day, a victory for workers in the mid-late 19th century.
2019-12-25 | Christmas Day | Christmas Day is an annual holiday which celebrates the birth of Jesus Christ over 2000 years ago.
2019-12-26 | Boxing Day | Boxing Day occurs the day after Christmas. Sydney-to-Hobart yacht race and Boxing Day Test Match (Cricket) start on this day.