## staff
id_staff | staff_name | staff_capacity | joined | departed
1 | Shelby | 40
2 | Luis | 60
3 | Taishawn | 100
4 | Samantha | 100
5 | Taylor | 100
6 | unassigned | 0

## projects
id_project | project_name | project_confirmed | project_start | project_end
1 | A | 0 | 2019-01-25 | 2019-06-03
2 | B | 1 | 2019-05-17 | 2019-06-16
3 | C | 1 | 2019-06-27 | 2019-09-27

## project_phases
id_project_phase | project_phase_name
1 | research
2 | drafting
3 | editing
4 | design
5 | print
6 | events

## out_of_office
id_out_of_office | staff_name | out_of_office_start | out_of_office_end | work_related
1 | Luis | 2019-07-23 | 2019-08-12 | 1
2 | Samantha | 2019-05-16 | 2019-06-10 | 0

## public_holidays
id_public_holidays | date | holiday_name
1 | 2019-01-01 | New Year's Day
2 | 2019-01-28 | Australia Day
3 | 2019-04-19 | Good Friday
4 | 2019-04-20 | Saturday before Easter Sunday
5 | 2019-04-21 | Easter Sunday
6 | 2019-04-22 | Easter Monday
7 | 2019-04-25 | Anzac Day
8 | 2019-06-10 | Queen's Birthday
9 | 2019-08-05 | Bank Holiday
10 | 2019-10-07 | Labour Day
11 | 2019-12-25 | Christmas Day
12 | 2019-12-26 | Boxing Day

## time_estimates
project_name | project_start | project_end | project_confirmed | research | drafting | editing | design | print | events
A | 2019-01-25 | 2019-06-03 | 0 | -10 | -10 | -10 | -10 | -10 | 10
B | 2019-05-17 | 2019-06-16 | 1 | -10 | -10 | -10 | -10 | -10 | 10
C | 2019-06-27 | 2019-09-27 | 1 | -10 | -10 | -10 | -10 | -10 | 10

## project_assignments
project_name | staff_name | staff_capacity | research | drafting | editing | design | print | events
A | Luis | 60 | 100 | 0 | 50 | 50 | 75 | 100
A | Samantha | 100 | 25 | 75 | 100 | 25 | 75 | 0
A | Shelby | 40 | 100 | 0 | 100 | 0 | 50 | 75
A | Taishawn | 100 | 50 | 50 | 25 | 25 | 50 | 25
A | Taylor | 100 | 25 | 0 | 25 | 100 | 75 | 50
A | unassigned | 0 | 100 | 25 | 50 | 75 | 100 | 0
B | Luis | 60 | 0 | 0 | 50 | 75 | 100 | 100
B | Samantha | 100 | 100 | 25 | 25 | 25 | 50 | 25
B | Shelby | 40 | 25 | 25 | 0 | 50 | 100 | 0
B | Taishawn | 100 | 0 | 50 | 75 | 100 | 50 | 25
B | Taylor | 100 | 100 | 50 | 0 | 50 | 75 | 75
B | unassigned | 0 | 100 | 75 | 25 | 100 | 25 | 50
C | Luis | 60 | 50 | 100 | 75 | 25 | 25 | 50
C | Samantha | 100 | 25 | 75 | 100 | 50 | 25 | 25
C | Shelby | 40 | 0 | 50 | 0 | 25 | 100 | 0
C | Taishawn | 100 | 75 | 75 | 100 | 50 | 0 | 100
C | Taylor | 100 | 75 | 25 | 75 | 50 | 25 | 100
C | unassigned | 0 | 0 | 75 | 100 | 100 | 0 | 0

## calendar
id_calendar | date
1 | 2018-09-27
2 | 2018-09-28
3 | 2018-10-01
4 | 2018-10-02
5 | 2018-10-03
6 | 2018-10-04
7 | 2018-10-05
8 | 2018-10-08
9 | 2018-10-09
10 | 2018-10-10
11 | 2018-10-11
12 | 2018-10-12
13 | 2018-10-15
14 | 2018-10-16
15 | 2018-10-17
16 | 2018-10-18
17 | 2018-10-19
18 | 2018-10-22
19 | 2018-10-23
20 | 2018-10-24
21 | 2018-10-25
22 | 2018-10-26
23 | 2018-10-29
24 | 2018-10-30
25 | 2018-10-31
26 | 2018-11-01
27 | 2018-11-02
28 | 2018-11-05
29 | 2018-11-06
30 | 2018-11-07
31 | 2018-11-08
32 | 2018-11-09
33 | 2018-11-12
34 | 2018-11-13
35 | 2018-11-14
36 | 2018-11-15
37 | 2018-11-16
38 | 2018-11-19
39 | 2018-11-20
40 | 2018-11-21
41 | 2018-11-22
42 | 2018-11-23
43 | 2018-11-26
44 | 2018-11-27
45 | 2018-11-28
46 | 2018-11-29
47 | 2018-11-30
48 | 2018-12-03
49 | 2018-12-04
50 | 2018-12-05
51 | 2018-12-06
52 | 2018-12-07
53 | 2018-12-10
54 | 2018-12-11
55 | 2018-12-12
56 | 2018-12-13
57 | 2018-12-14
58 | 2018-12-17
59 | 2018-12-18
60 | 2018-12-19
61 | 2018-12-20
62 | 2018-12-21
63 | 2018-12-24
64 | 2018-12-25
65 | 2018-12-26
66 | 2018-12-27
67 | 2018-12-28
68 | 2018-12-31
69 | 2019-01-01
70 | 2019-01-02
71 | 2019-01-03
72 | 2019-01-04
73 | 2019-01-07
74 | 2019-01-08
75 | 2019-01-09
76 | 2019-01-10
77 | 2019-01-11
78 | 2019-01-14
79 | 2019-01-15
80 | 2019-01-16
81 | 2019-01-17
82 | 2019-01-18
83 | 2019-01-21
84 | 2019-01-22
85 | 2019-01-23
86 | 2019-01-24
87 | 2019-01-25
88 | 2019-01-28
89 | 2019-01-29
90 | 2019-01-30
91 | 2019-01-31
92 | 2019-02-01
93 | 2019-02-04
94 | 2019-02-05
95 | 2019-02-06
96 | 2019-02-07
97 | 2019-02-08
98 | 2019-02-11
99 | 2019-02-12
100 | 2019-02-13
101 | 2019-02-14
102 | 2019-02-15
103 | 2019-02-18
104 | 2019-02-19
105 | 2019-02-20
106 | 2019-02-21
107 | 2019-02-22
108 | 2019-02-25
109 | 2019-02-26
110 | 2019-02-27
111 | 2019-02-28
112 | 2019-03-01
113 | 2019-03-04
114 | 2019-03-05
115 | 2019-03-06
116 | 2019-03-07
117 | 2019-03-08
118 | 2019-03-11
119 | 2019-03-12
120 | 2019-03-13
121 | 2019-03-14
122 | 2019-03-15
123 | 2019-03-18
124 | 2019-03-19
125 | 2019-03-20
126 | 2019-03-21
127 | 2019-03-22
128 | 2019-03-25
129 | 2019-03-26
130 | 2019-03-27
131 | 2019-03-28
132 | 2019-03-29
133 | 2019-04-01
134 | 2019-04-02
135 | 2019-04-03
136 | 2019-04-04
137 | 2019-04-05
138 | 2019-04-08
139 | 2019-04-09
140 | 2019-04-10
141 | 2019-04-11
142 | 2019-04-12
143 | 2019-04-15
144 | 2019-04-16
145 | 2019-04-17
146 | 2019-04-18
147 | 2019-04-19
148 | 2019-04-22
149 | 2019-04-23
150 | 2019-04-24
151 | 2019-04-25
152 | 2019-04-26
153 | 2019-04-29
154 | 2019-04-30
155 | 2019-05-01
156 | 2019-05-02
157 | 2019-05-03
158 | 2019-05-06
159 | 2019-05-07
160 | 2019-05-08
161 | 2019-05-09
162 | 2019-05-10
163 | 2019-05-13
164 | 2019-05-14
165 | 2019-05-15
166 | 2019-05-16
167 | 2019-05-17
168 | 2019-05-20
169 | 2019-05-21
170 | 2019-05-22
171 | 2019-05-23
172 | 2019-05-24
173 | 2019-05-27
174 | 2019-05-28
175 | 2019-05-29
176 | 2019-05-30
177 | 2019-05-31
178 | 2019-06-03
179 | 2019-06-04
180 | 2019-06-05
181 | 2019-06-06
182 | 2019-06-07
183 | 2019-06-10
184 | 2019-06-11
185 | 2019-06-12
186 | 2019-06-13
187 | 2019-06-14
188 | 2019-06-17
189 | 2019-06-18
190 | 2019-06-19
191 | 2019-06-20
192 | 2019-06-21
193 | 2019-06-24
194 | 2019-06-25
195 | 2019-06-26
196 | 2019-06-27
197 | 2019-06-28
198 | 2019-07-01
199 | 2019-07-02
200 | 2019-07-03
201 | 2019-07-04
202 | 2019-07-05
203 | 2019-07-08
204 | 2019-07-09
205 | 2019-07-10
206 | 2019-07-11
207 | 2019-07-12
208 | 2019-07-15
209 | 2019-07-16
210 | 2019-07-17
211 | 2019-07-18
212 | 2019-07-19
213 | 2019-07-22
214 | 2019-07-23
215 | 2019-07-24
216 | 2019-07-25
217 | 2019-07-26
218 | 2019-07-29
219 | 2019-07-30
220 | 2019-07-31
221 | 2019-08-01
222 | 2019-08-02
223 | 2019-08-05
224 | 2019-08-06
225 | 2019-08-07
226 | 2019-08-08
227 | 2019-08-09
228 | 2019-08-12
229 | 2019-08-13
230 | 2019-08-14
231 | 2019-08-15
232 | 2019-08-16
233 | 2019-08-19
234 | 2019-08-20
235 | 2019-08-21
236 | 2019-08-22
237 | 2019-08-23
238 | 2019-08-26
239 | 2019-08-27
240 | 2019-08-28
241 | 2019-08-29
242 | 2019-08-30
243 | 2019-09-02
244 | 2019-09-03
245 | 2019-09-04
246 | 2019-09-05
247 | 2019-09-06
248 | 2019-09-09
249 | 2019-09-10
250 | 2019-09-11
251 | 2019-09-12
252 | 2019-09-13
253 | 2019-09-16
254 | 2019-09-17
255 | 2019-09-18
256 | 2019-09-19
257 | 2019-09-20
258 | 2019-09-23
259 | 2019-09-24
260 | 2019-09-25
261 | 2019-09-26
262 | 2019-09-27
263 | 2019-09-30
264 | 2019-10-01
265 | 2019-10-02
266 | 2019-10-03
267 | 2019-10-04
268 | 2019-10-07
269 | 2019-10-08
270 | 2019-10-09
271 | 2019-10-10
272 | 2019-10-11
273 | 2019-10-14
274 | 2019-10-15
275 | 2019-10-16
276 | 2019-10-17
277 | 2019-10-18
278 | 2019-10-21
279 | 2019-10-22
280 | 2019-10-23
281 | 2019-10-24
282 | 2019-10-25