## resources
staff | capacity | contract
andrea | 40 | fte
delanie | 100 | intern
harrison | 100 | fte
hunter | 100 | intern
isabella | 100 | intern
mohib | 100 | fte
murray | 100 | fte
nick | 100 | intern
paulo | 100 | fte
steve | 100 | fte
talia | 100 | fte
thom | 100 | fte
unassigned | 100 | fte
wallace | 100 | fte
zak | 100 | fte

## projects
project | probability.of.occuring | kickoff | launch
DFAT | 1 | 2019-01-18 11:00 | 2019-02-18 11:00
UNDP Addis | 1 | 2019-01-21 11:00 | 2019-02-27 11:00
SDG16 | 1 | 2019-01-18 11:00 | 2019-03-18 11:00
Finance and Peace | 1 | 2019-01-18 11:00 | 2019-03-21 11:00
KAS | 0.5 | 2019-02-18 11:00 | 2019-03-28 11:00
MPI | 1 | 2019-01-18 11:00 | 2019-04-09 11:00
CEF | 1 | 2019-01-25 11:00 | 2019-05-01 11:00
GPI | 1 | 2019-02-20 11:00 | 2019-05-30 11:00
Normandy Peace Index | 0.5 | 2019-03-01 11:00 | 2019-06-06 11:00
WISPI Update | 0.5 | 2019-04-01 11:00 | 2019-06-06 11:00
maintenance | 1 | 2019-02-01 11:00 | 2019-06-30 11:00
Risk Paper | 1 | 2019-05-30 11:00 | 2019-07-31 11:00
SESHAT | 1 | 2019-06-01 11:00 | 2019-09-30 11:00
PPI | 1 | 2019-08-01 11:00 | 2019-10-30 11:00
GTI | 1 | 2019-08-01 11:00 | 2019-11-25 11:00

## phases
id | phases | dependencies
1 | research | 0
2 | drafting | 1
3 | editing | 2
4 | design | 3
5 | print | 4
6 | events | 5

## roles
roles
lead
researcher
editor
design

## leave
name | start | end | description
thom | 2019-02-11 11:00 | 2019-02-22 11:00 | leave
steve | 2019-03-03 11:00 | 2019-03-08 11:00 | Melbourne
steve | 2019-03-25 11:00 | 2019-04-15 11:00 | Oslo
steve | 2019-05-13 11:00 | 2019-07-01 11:00 | GPI

## holidays
holiday | holiday.dates
New Year's Day | 2019-01-01 11:00
2Australia Day | 2019-01-28 11:00
Good Friday | 2019-04-19 11:00
Easter Saturday | 2019-04-20 11:00
Easter Sunday | 2019-04-21 11:00
Easter Monday | 2019-04-22 11:00
Anzac Day | 2019-04-25 11:00
Queen's Birthday | 2019-06-10 11:00
1Bank Holiday | 2019-08-05 11:00
Labour Day | 2019-10-07 11:00
Christmas Day | 2019-12-25 11:00
Boxing Day | 2019-12-26 11:00

## teams
project | staff | role | workshare
DFAT | andrea
DFAT | delanie
DFAT | harrison
DFAT | hunter
DFAT | isabella
DFAT | mohib
DFAT | murray | lead | 100
DFAT | nick
DFAT | paulo
DFAT | steve
DFAT | talia
DFAT | thom
DFAT | unassigned
DFAT | wallace
DFAT | zak
UNDP Addis | andrea | lead | 100
UNDP Addis | delanie
UNDP Addis | harrison
UNDP Addis | hunter
UNDP Addis | isabella
UNDP Addis | mohib
UNDP Addis | murray
UNDP Addis | nick
UNDP Addis | paulo
UNDP Addis | steve
UNDP Addis | talia
UNDP Addis | thom
UNDP Addis | unassigned
UNDP Addis | wallace
UNDP Addis | zak
SDG16 | andrea
SDG16 | delanie
SDG16 | harrison | researcher
SDG16 | hunter
SDG16 | isabella
SDG16 | mohib
SDG16 | murray
SDG16 | nick
SDG16 | paulo
SDG16 | steve | editor
SDG16 | talia | lead
SDG16 | thom
SDG16 | unassigned
SDG16 | wallace | design
SDG16 | zak
Finance and Peace | andrea
Finance and Peace | delanie
Finance and Peace | harrison
Finance and Peace | hunter
Finance and Peace | isabella
Finance and Peace | mohib
Finance and Peace | murray
Finance and Peace | nick
Finance and Peace | paulo | lead
Finance and Peace | steve
Finance and Peace | talia
Finance and Peace | thom
Finance and Peace | unassigned
Finance and Peace | wallace
Finance and Peace | zak
KAS | andrea
KAS | delanie
KAS | harrison
KAS | hunter
KAS | isabella
KAS | mohib
KAS | murray | lead
KAS | nick
KAS | paulo
KAS | steve
KAS | talia
KAS | thom
KAS | unassigned
KAS | wallace
KAS | zak
MPI | andrea
MPI | delanie | researcher
MPI | harrison | researcher
MPI | hunter
MPI | isabella
MPI | mohib | researcher
MPI | murray
MPI | nick | researcher
MPI | paulo
MPI | steve | editor
MPI | talia | lead
MPI | thom
MPI | unassigned
MPI | wallace | design
MPI | zak
CEF | andrea
CEF | delanie
CEF | harrison
CEF | hunter
CEF | isabella
CEF | mohib | researcher
CEF | murray
CEF | nick
CEF | paulo
CEF | steve | editor
CEF | talia
CEF | thom
CEF | unassigned
CEF | wallace | design
CEF | zak | researcher
GPI | andrea
GPI | delanie
GPI | harrison | researcher
GPI | hunter | researcher
GPI | isabella | researcher
GPI | mohib | researcher
GPI | murray
GPI | nick
GPI | paulo | researcher
GPI | steve | editor
GPI | talia
GPI | thom | lead
GPI | unassigned
GPI | wallace | design
GPI | zak | researcher
Normandy Peace Index | andrea
Normandy Peace Index | delanie
Normandy Peace Index | harrison
Normandy Peace Index | hunter
Normandy Peace Index | isabella
Normandy Peace Index | mohib
Normandy Peace Index | murray
Normandy Peace Index | nick
Normandy Peace Index | paulo
Normandy Peace Index | steve
Normandy Peace Index | talia
Normandy Peace Index | thom
Normandy Peace Index | unassigned | lead
Normandy Peace Index | wallace
Normandy Peace Index | zak
WISPI Update | andrea
WISPI Update | delanie
WISPI Update | harrison
WISPI Update | hunter
WISPI Update | isabella
WISPI Update | mohib
WISPI Update | murray
WISPI Update | nick
WISPI Update | paulo
WISPI Update | steve
WISPI Update | talia
WISPI Update | thom
WISPI Update | unassigned | lead
WISPI Update | wallace
WISPI Update | zak
maintenance | andrea
maintenance | delanie
maintenance | harrison
maintenance | hunter
maintenance | isabella
maintenance | mohib
maintenance | murray
maintenance | nick
maintenance | paulo
maintenance | steve
maintenance | talia
maintenance | thom
maintenance | unassigned
maintenance | wallace
maintenance | zak | lead
Risk Paper | andrea
Risk Paper | delanie
Risk Paper | harrison
Risk Paper | hunter
Risk Paper | isabella
Risk Paper | mohib
Risk Paper | murray
Risk Paper | nick
Risk Paper | paulo
Risk Paper | steve
Risk Paper | talia
Risk Paper | thom
Risk Paper | unassigned | lead
Risk Paper | wallace | design
Risk Paper | zak
SESHAT | andrea
SESHAT | delanie
SESHAT | harrison
SESHAT | hunter
SESHAT | isabella
SESHAT | mohib
SESHAT | murray
SESHAT | nick
SESHAT | paulo
SESHAT | steve
SESHAT | talia
SESHAT | thom | lead
SESHAT | unassigned | researcher
SESHAT | wallace | design
SESHAT | zak
PPI | andrea
PPI | delanie
PPI | harrison
PPI | hunter
PPI | isabella
PPI | mohib
PPI | murray
PPI | nick
PPI | paulo | researcher
PPI | steve | editor
PPI | talia | lead
PPI | thom
PPI | unassigned
PPI | wallace | design
PPI | zak | researcher
GTI | andrea
GTI | delanie
GTI | harrison
GTI | hunter
GTI | isabella
GTI | mohib | researcher
GTI | murray | researcher
GTI | nick
GTI | paulo
GTI | steve | editor
GTI | talia
GTI | thom | lead
GTI | unassigned
GTI | wallace | design
GTI | zak

## responsibilities
roles | research | drafting | editing | design | print | events
lead | 1 | 1 | 1 | 1 | 1 | 1
researcher | 1 | 1 | 1
editor |  |  | 1 |  |  | 1
design |  |  |  | 1

## time.estimates
projects | drafting | editing | design | print | events
DFAT | 0 | 0 | 10 | 5 | 5
UNDP Addis | 10 | 0 | 0 | 0 | 0
SDG16 | 10 | 15 | 15 | 8 | 5
Finance and Peace | 0 | 0 | 0 | 0 | 0
KAS | 10 | 0 | 0 | 0 | 0
MPI | 10 | 10 | 20 | 8 | 5
CEF | 10 | 10 | 15 | 5 | 0
GPI | 15 | 15 | 15 | 8 | 5
Normandy Peace Index | 10 | 10 | 0 | 0 | 0
WISPI Update | 10 | 10 | 0 | 0 | 0
maintenance | 0 | 0 | 0 | 0 | 0
Risk Paper | 10 | 10 | 5 | 5 | 0
SESHAT | 10 | 10 | 15 | 5 | 5
PPI | 15 | 15 | 15 | 8 | 5
GTI | 15 | 15 | 15 | 8 | 5