## staff
id_staff | staff_name | staff_capacity
1 | andrea | 40
2 | delanie | 100
3 | harrison | 100
4 | hunter | 100
5 | isabella | 100
6 | mohib | 100
7 | murray | 100
8 | nick | 100
9 | paulo | 100
10 | steve | 100
11 | talia | 100
12 | thom | 100
13 | wallace | 100
14 | zak | 100

## projects
id_project | project_name | project_confirmed | project_start | project_end
1 | SDG16 | TRUE | 2019-01-18 | 2019-03-18
2 | DFAT | TRUE | 2019-01-18 | 2019-02-18
3 | MPI | TRUE | 2019-01-18 | 2019-04-09
4 | CEF | TRUE | 2019-01-25 | 2019-05-01
5 | Risk Paper | TRUE | 2019-05-30 | 2019-07-31
6 | GPI | TRUE | 2019-02-20 | 2019-05-30
7 | Normandy Peace Index | FALSE | 2019-03-01 | 2019-06-06
8 | WISPI Update | FALSE | 2019-04-01 | 2019-06-06
9 | UNDP Addis | TRUE | 2019-01-21 | 2019-02-27
10 | Finance and Peace | TRUE | 2019-01-18 | 2019-03-21
11 | PPI | TRUE | 2019-08-01 | 2019-10-30
12 | GTI | TRUE | 2019-08-01 | 2019-11-25
13 | SESHAT | TRUE | 2019-06-01 | 2019-09-30
14 | KAS | FALSE | 2019-02-18 | 2019-03-28
15 | maintenance | TRUE | 2019-02-01 | 2019-06-30

## project_phases
id_project_phase | project_phase_name
1 | research
2 | drafting
3 | editing
4 | design
5 | print
6 | events

## out_of_office
id_out_of_office | staff_name | out_of_office_start | out_of_office_end | work_related
1 | thom | 2019-02-11 | 2019-02-22 | 0
2 | steve | 2019-03-03 | 2019-03-08 | 1
3 | steve | 2019-03-25 | 2019-04-15 | 1
4 | steve | 2019-05-13 | 2019-07-01 | 1
Formulas:
out_of_office_end = [out_of_office_start]+7*7

## public_holidays
id_public_holidays | date | holiday_name
1 | 2019-01-01 | New Year's Day
2 | 2019-01-28 | Australia Day
3 | 2019-04-19 | Good Friday
4 | 2019-04-20 | Saturday before Easter Sunday
5 | 2019-04-21 | Easter Sunday
6 | 2019-04-22 | Easter Monday
7 | 2019-04-25 | Anzac Day
8 | 2019-06-10 | Queen's Birthday
9 | 2019-08-05 | Bank Holiday
10 | 2019-10-07 | Labour Day
11 | 2019-12-25 | Christmas Day
12 | 2019-12-26 | Boxing Day

## time_estimates
project_name | project_start | project_end | project_confirmed | research | drafting | editing | design | print | events
SDG16 | 2019-01-18 | 2019-03-18 | TRUE | -10 | -10 | -10 | -10 | -5 | 0
DFAT | 2019-01-18 | 2019-02-18 | TRUE | 0 | 0 | 0 | -10 | -8 | 1
MPI | 2019-01-18 | 2019-04-09 | TRUE | -10 | -10 | -10 | -25 | -10 | 5
CEF | 2019-01-25 | 2019-05-01 | TRUE | -10 | -10 | -10 | -10 | -10 | 0
Risk Paper | 2019-05-30 | 2019-07-31 | TRUE | -10 | -10 | -10 | -10 | -10 | 0
GPI | 2019-02-20 | 2019-05-30 | TRUE | -10 | -10 | -10 | -15 | -10 | 10
Normandy Peace Index | 2019-03-01 | 2019-06-06 | FALSE | -10 | -10 | -10 | 0 | 0 | 0
WISPI Update | 2019-04-01 | 2019-06-06 | FALSE | -10 | -10 | -5 | 0 | 0 | 0
UNDP Addis | 2019-01-21 | 2019-02-27 | TRUE | -10 | 0 | -5 | 0 | 0 | 0
Finance and Peace | 2019-01-18 | 2019-03-21 | TRUE | -10 | -10 | -10 | 0 | 0 | 0
PPI | 2019-08-01 | 2019-10-30 | TRUE | -10 | -10 | -10 | -15 | -10 | 10
GTI | 2019-08-01 | 2019-11-25 | TRUE | -10 | -10 | -10 | -15 | -10 | 10
SESHAT | 2019-06-01 | 2019-09-30 | TRUE | -10 | -10 | -10 | -10 | -10 | 5
KAS | 2019-02-18 | 2019-03-28 | FALSE | -10 | 0 | 0 | 0 | 0 | 5
maintenance | 2019-02-01 | 2019-06-30 | TRUE | -10 | 0 | 0 | 0 | 0 | 0

## calendar
id_calendar | date
1 | 2010-01-01
2 | 2010-01-04
3 | 2010-01-05
4 | 2010-01-06
5 | 2010-01-07
6 | 2010-01-08
7 | 2010-01-11
8 | 2010-01-12
9 | 2010-01-13
10 | 2010-01-14
11 | 2010-01-15
12 | 2010-01-18
13 | 2010-01-19
14 | 2010-01-20
15 | 2010-01-21
16 | 2010-01-22
17 | 2010-01-25
18 | 2010-01-26
19 | 2010-01-27
20 | 2010-01-28
21 | 2010-01-29
22 | 2010-02-01
23 | 2010-02-02
24 | 2010-02-03
25 | 2010-02-04
26 | 2010-02-05
27 | 2010-02-08
28 | 2010-02-09
29 | 2010-02-10
30 | 2010-02-11
31 | 2010-02-12
32 | 2010-02-15
33 | 2010-02-16
34 | 2010-02-17
35 | 2010-02-18
36 | 2010-02-19
37 | 2010-02-22
38 | 2010-02-23
39 | 2010-02-24
40 | 2010-02-25
41 | 2010-02-26
42 | 2010-03-01
43 | 2010-03-02
44 | 2010-03-03
45 | 2010-03-04
46 | 2010-03-05
47 | 2010-03-08
48 | 2010-03-09
49 | 2010-03-10
50 | 2010-03-11
51 | 2010-03-12
52 | 2010-03-15
53 | 2010-03-16
54 | 2010-03-17
55 | 2010-03-18
56 | 2010-03-19
57 | 2010-03-22
58 | 2010-03-23
59 | 2010-03-24
60 | 2010-03-25
61 | 2010-03-26
62 | 2010-03-29
63 | 2010-03-30
64 | 2010-03-31
65 | 2010-04-01
66 | 2010-04-02
67 | 2010-04-05
68 | 2010-04-06
69 | 2010-04-07
70 | 2010-04-08
71 | 2010-04-09
72 | 2010-04-12
73 | 2010-04-13
74 | 2010-04-14
75 | 2010-04-15
76 | 2010-04-16
77 | 2010-04-19
78 | 2010-04-20
79 | 2010-04-21
80 | 2010-04-22
81 | 2010-04-23
82 | 2010-04-26
83 | 2010-04-27
84 | 2010-04-28
85 | 2010-04-29
86 | 2010-04-30
87 | 2010-05-03
88 | 2010-05-04
89 | 2010-05-05
90 | 2010-05-06
91 | 2010-05-07
92 | 2010-05-10
93 | 2010-05-11
94 | 2010-05-12
95 | 2010-05-13
96 | 2010-05-14
97 | 2010-05-17
98 | 2010-05-18
99 | 2010-05-19
100 | 2010-05-20
101 | 2010-05-21
102 | 2010-05-24
103 | 2010-05-25
104 | 2010-05-26
105 | 2010-05-27
106 | 2010-05-28
107 | 2010-05-31
108 | 2010-06-01
109 | 2010-06-02
110 | 2010-06-03
111 | 2010-06-04
112 | 2010-06-07
113 | 2010-06-08
114 | 2010-06-09
115 | 2010-06-10
116 | 2010-06-11
117 | 2010-06-14
118 | 2010-06-15
119 | 2010-06-16
120 | 2010-06-17
121 | 2010-06-18
122 | 2010-06-21
123 | 2010-06-22
124 | 2010-06-23
125 | 2010-06-24
126 | 2010-06-25
127 | 2010-06-28
128 | 2010-06-29
129 | 2010-06-30
130 | 2010-07-01
131 | 2010-07-02
132 | 2010-07-05
133 | 2010-07-06
134 | 2010-07-07
135 | 2010-07-08
136 | 2010-07-09
137 | 2010-07-12
138 | 2010-07-13
139 | 2010-07-14
140 | 2010-07-15
141 | 2010-07-16
142 | 2010-07-19
143 | 2010-07-20
144 | 2010-07-21
145 | 2010-07-22
146 | 2010-07-23
147 | 2010-07-26
148 | 2010-07-27
149 | 2010-07-28
150 | 2010-07-29
151 | 2010-07-30
152 | 2010-08-02
153 | 2010-08-03
154 | 2010-08-04
155 | 2010-08-05
156 | 2010-08-06
157 | 2010-08-09
158 | 2010-08-10
159 | 2010-08-11
160 | 2010-08-12
161 | 2010-08-13
162 | 2010-08-16
163 | 2010-08-17
164 | 2010-08-18
165 | 2010-08-19
166 | 2010-08-20
167 | 2010-08-23
168 | 2010-08-24
169 | 2010-08-25
170 | 2010-08-26
171 | 2010-08-27
172 | 2010-08-30
173 | 2010-08-31
174 | 2010-09-01
175 | 2010-09-02
176 | 2010-09-03
177 | 2010-09-06
178 | 2010-09-07
179 | 2010-09-08
180 | 2010-09-09
181 | 2010-09-10
182 | 2010-09-13
183 | 2010-09-14
184 | 2010-09-15
185 | 2010-09-16
186 | 2010-09-17
187 | 2010-09-20
188 | 2010-09-21
189 | 2010-09-22
190 | 2010-09-23
191 | 2010-09-24
192 | 2010-09-27
193 | 2010-09-28
194 | 2010-09-29
195 | 2010-09-30
196 | 2010-10-01
197 | 2010-10-04
198 | 2010-10-05
199 | 2010-10-06
200 | 2010-10-07
201 | 2010-10-08
202 | 2010-10-11
203 | 2010-10-12
204 | 2010-10-13
205 | 2010-10-14
206 | 2010-10-15
207 | 2010-10-18
208 | 2010-10-19
209 | 2010-10-20
210 | 2010-10-21
211 | 2010-10-22
212 | 2010-10-25
213 | 2010-10-26
214 | 2010-10-27
215 | 2010-10-28
216 | 2010-10-29
217 | 2010-11-01
218 | 2010-11-02
219 | 2010-11-03
220 | 2010-11-04
221 | 2010-11-05
222 | 2010-11-08
223 | 2010-11-09
224 | 2010-11-10
225 | 2010-11-11
226 | 2010-11-12
227 | 2010-11-15
228 | 2010-11-16
229 | 2010-11-17
230 | 2010-11-18
231 | 2010-11-19
232 | 2010-11-22
233 | 2010-11-23
234 | 2010-11-24
235 | 2010-11-25
236 | 2010-11-26
237 | 2010-11-29
238 | 2010-11-30
239 | 2010-12-01
240 | 2010-12-02
241 | 2010-12-03
242 | 2010-12-06
243 | 2010-12-07
244 | 2010-12-08
245 | 2010-12-09
246 | 2010-12-10
247 | 2010-12-13
248 | 2010-12-14
249 | 2010-12-15
250 | 2010-12-16
251 | 2010-12-17
252 | 2010-12-20
253 | 2010-12-21
254 | 2010-12-22
255 | 2010-12-23
256 | 2010-12-24
257 | 2010-12-27
258 | 2010-12-28
259 | 2010-12-29
260 | 2010-12-30
261 | 2010-12-31
262 | 2011-01-03
263 | 2011-01-04
264 | 2011-01-05
265 | 2011-01-06
266 | 2011-01-07
267 | 2011-01-10
268 | 2011-01-11
269 | 2011-01-12
270 | 2011-01-13
271 | 2011-01-14
272 | 2011-01-17
273 | 2011-01-18
274 | 2011-01-19
275 | 2011-01-20
276 | 2011-01-21
277 | 2011-01-24
278 | 2011-01-25
279 | 2011-01-26
280 | 2011-01-27
281 | 2011-01-28
282 | 2011-01-31
283 | 2011-02-01
284 | 2011-02-02
285 | 2011-02-03
286 | 2011-02-04
287 | 2011-02-07
288 | 2011-02-08
289 | 2011-02-09
290 | 2011-02-10
291 | 2011-02-11
292 | 2011-02-14
293 | 2011-02-15
294 | 2011-02-16
295 | 2011-02-17
296 | 2011-02-18
297 | 2011-02-21
298 | 2011-02-22
299 | 2011-02-23
300 | 2011-02-24
301 | 2011-02-25
302 | 2011-02-28
303 | 2011-03-01
304 | 2011-03-02
305 | 2011-03-03
306 | 2011-03-04
307 | 2011-03-07
308 | 2011-03-08
309 | 2011-03-09
310 | 2011-03-10
311 | 2011-03-11
312 | 2011-03-14
313 | 2011-03-15
314 | 2011-03-16
315 | 2011-03-17
316 | 2011-03-18
317 | 2011-03-21
318 | 2011-03-22
319 | 2011-03-23
320 | 2011-03-24
321 | 2011-03-25
322 | 2011-03-28
323 | 2011-03-29
324 | 2011-03-30
325 | 2011-03-31
326 | 2011-04-01
327 | 2011-04-04
328 | 2011-04-05
329 | 2011-04-06
330 | 2011-04-07
331 | 2011-04-08
332 | 2011-04-11
333 | 2011-04-12
334 | 2011-04-13
335 | 2011-04-14
336 | 2011-04-15
337 | 2011-04-18
338 | 2011-04-19
339 | 2011-04-20
340 | 2011-04-21
341 | 2011-04-22
342 | 2011-04-25
343 | 2011-04-26
344 | 2011-04-27
345 | 2011-04-28
346 | 2011-04-29
347 | 2011-05-02
348 | 2011-05-03
349 | 2011-05-04
350 | 2011-05-05
351 | 2011-05-06
352 | 2011-05-09
353 | 2011-05-10
354 | 2011-05-11
355 | 2011-05-12
356 | 2011-05-13
357 | 2011-05-16
358 | 2011-05-17
359 | 2011-05-18
360 | 2011-05-19
361 | 2011-05-20
362 | 2011-05-23
363 | 2011-05-24
364 | 2011-05-25
365 | 2011-05-26
366 | 2011-05-27
367 | 2011-05-30
368 | 2011-05-31
369 | 2011-06-01
370 | 2011-06-02
371 | 2011-06-03
372 | 2011-06-06
373 | 2011-06-07
374 | 2011-06-08
375 | 2011-06-09
376 | 2011-06-10
377 | 2011-06-13
378 | 2011-06-14
379 | 2011-06-15
380 | 2011-06-16
381 | 2011-06-17
382 | 2011-06-20
383 | 2011-06-21
384 | 2011-06-22
385 | 2011-06-23
386 | 2011-06-24
387 | 2011-06-27
388 | 2011-06-28
389 | 2011-06-29
390 | 2011-06-30
391 | 2011-07-01
392 | 2011-07-04
393 | 2011-07-05
394 | 2011-07-06
395 | 2011-07-07
396 | 2011-07-08
397 | 2011-07-11
398 | 2011-07-12
399 | 2011-07-13
400 | 2011-07-14
401 | 2011-07-15
402 | 2011-07-18
403 | 2011-07-19
404 | 2011-07-20
405 | 2011-07-21
406 | 2011-07-22
407 | 2011-07-25
408 | 2011-07-26
409 | 2011-07-27
410 | 2011-07-28
411 | 2011-07-29
412 | 2011-08-01
413 | 2011-08-02
414 | 2011-08-03
415 | 2011-08-04
416 | 2011-08-05
417 | 2011-08-08
418 | 2011-08-09
419 | 2011-08-10
420 | 2011-08-11
421 | 2011-08-12
422 | 2011-08-15
423 | 2011-08-16
424 | 2011-08-17
425 | 2011-08-18
426 | 2011-08-19
427 | 2011-08-22
428 | 2011-08-23
429 | 2011-08-24
430 | 2011-08-25
431 | 2011-08-26
432 | 2011-08-29
433 | 2011-08-30
434 | 2011-08-31
435 | 2011-09-01
436 | 2011-09-02
437 | 2011-09-05
438 | 2011-09-06
439 | 2011-09-07
440 | 2011-09-08
441 | 2011-09-09
442 | 2011-09-12
443 | 2011-09-13
444 | 2011-09-14
445 | 2011-09-15
446 | 2011-09-16
447 | 2011-09-19
448 | 2011-09-20
449 | 2011-09-21
450 | 2011-09-22
451 | 2011-09-23
452 | 2011-09-26
453 | 2011-09-27
454 | 2011-09-28
455 | 2011-09-29
456 | 2011-09-30
457 | 2011-10-03
458 | 2011-10-04
459 | 2011-10-05
460 | 2011-10-06
461 | 2011-10-07
462 | 2011-10-10
463 | 2011-10-11
464 | 2011-10-12
465 | 2011-10-13
466 | 2011-10-14
467 | 2011-10-17
468 | 2011-10-18
469 | 2011-10-19
470 | 2011-10-20
471 | 2011-10-21
472 | 2011-10-24
473 | 2011-10-25
474 | 2011-10-26
475 | 2011-10-27
476 | 2011-10-28
477 | 2011-10-31
478 | 2011-11-01
479 | 2011-11-02
480 | 2011-11-03
481 | 2011-11-04
482 | 2011-11-07
483 | 2011-11-08
484 | 2011-11-09
485 | 2011-11-10
486 | 2011-11-11
487 | 2011-11-14
488 | 2011-11-15
489 | 2011-11-16
490 | 2011-11-17
491 | 2011-11-18
492 | 2011-11-21
493 | 2011-11-22
494 | 2011-11-23
495 | 2011-11-24
496 | 2011-11-25
497 | 2011-11-28
498 | 2011-11-29
499 | 2011-11-30
500 | 2011-12-01
501 | 2011-12-02
502 | 2011-12-05
503 | 2011-12-06
504 | 2011-12-07
505 | 2011-12-08
506 | 2011-12-09
507 | 2011-12-12
508 | 2011-12-13
509 | 2011-12-14
510 | 2011-12-15
511 | 2011-12-16
512 | 2011-12-19
513 | 2011-12-20
514 | 2011-12-21
515 | 2011-12-22
516 | 2011-12-23
517 | 2011-12-26
518 | 2011-12-27
519 | 2011-12-28
520 | 2011-12-29
521 | 2011-12-30
522 | 2012-01-02
523 | 2012-01-03
524 | 2012-01-04
525 | 2012-01-05
526 | 2012-01-06
527 | 2012-01-09
528 | 2012-01-10
529 | 2012-01-11
530 | 2012-01-12
531 | 2012-01-13
532 | 2012-01-16
533 | 2012-01-17
534 | 2012-01-18
535 | 2012-01-19
536 | 2012-01-20
537 | 2012-01-23
538 | 2012-01-24
539 | 2012-01-25
540 | 2012-01-26
541 | 2012-01-27
542 | 2012-01-30
543 | 2012-01-31
544 | 2012-02-01
545 | 2012-02-02
546 | 2012-02-03
547 | 2012-02-06
548 | 2012-02-07
549 | 2012-02-08
550 | 2012-02-09
551 | 2012-02-10
552 | 2012-02-13
553 | 2012-02-14
554 | 2012-02-15
555 | 2012-02-16
556 | 2012-02-17
557 | 2012-02-20
558 | 2012-02-21
559 | 2012-02-22
560 | 2012-02-23
561 | 2012-02-24
562 | 2012-02-27
563 | 2012-02-28
564 | 2012-02-29
565 | 2012-03-01
566 | 2012-03-02
567 | 2012-03-05
568 | 2012-03-06
569 | 2012-03-07
570 | 2012-03-08
571 | 2012-03-09
572 | 2012-03-12
573 | 2012-03-13
574 | 2012-03-14
575 | 2012-03-15
576 | 2012-03-16
577 | 2012-03-19
578 | 2012-03-20
579 | 2012-03-21
580 | 2012-03-22
581 | 2012-03-23
582 | 2012-03-26
583 | 2012-03-27
584 | 2012-03-28
585 | 2012-03-29
586 | 2012-03-30
587 | 2012-04-02
588 | 2012-04-03
589 | 2012-04-04
590 | 2012-04-05
591 | 2012-04-06
592 | 2012-04-09
593 | 2012-04-10
594 | 2012-04-11
595 | 2012-04-12
596 | 2012-04-13
597 | 2012-04-16
598 | 2012-04-17
599 | 2012-04-18
600 | 2012-04-19
601 | 2012-04-20
602 | 2012-04-23
603 | 2012-04-24
604 | 2012-04-25
605 | 2012-04-26
606 | 2012-04-27
607 | 2012-04-30
608 | 2012-05-01
609 | 2012-05-02
610 | 2012-05-03
611 | 2012-05-04
612 | 2012-05-07
613 | 2012-05-08
614 | 2012-05-09
615 | 2012-05-10
616 | 2012-05-11
617 | 2012-05-14
618 | 2012-05-15
619 | 2012-05-16
620 | 2012-05-17
621 | 2012-05-18
622 | 2012-05-21
623 | 2012-05-22
624 | 2012-05-23
625 | 2012-05-24
626 | 2012-05-25
627 | 2012-05-28
628 | 2012-05-29
629 | 2012-05-30
630 | 2012-05-31
631 | 2012-06-01
632 | 2012-06-04
633 | 2012-06-05
634 | 2012-06-06
635 | 2012-06-07
636 | 2012-06-08
637 | 2012-06-11
638 | 2012-06-12
639 | 2012-06-13
640 | 2012-06-14
641 | 2012-06-15
642 | 2012-06-18
643 | 2012-06-19
644 | 2012-06-20
645 | 2012-06-21
646 | 2012-06-22
647 | 2012-06-25
648 | 2012-06-26
649 | 2012-06-27
650 | 2012-06-28
651 | 2012-06-29
652 | 2012-07-02
653 | 2012-07-03
654 | 2012-07-04
655 | 2012-07-05
656 | 2012-07-06
657 | 2012-07-09
658 | 2012-07-10
659 | 2012-07-11
660 | 2012-07-12
661 | 2012-07-13
662 | 2012-07-16
663 | 2012-07-17
664 | 2012-07-18
665 | 2012-07-19
666 | 2012-07-20
667 | 2012-07-23
668 | 2012-07-24
669 | 2012-07-25
670 | 2012-07-26
671 | 2012-07-27
672 | 2012-07-30
673 | 2012-07-31
674 | 2012-08-01
675 | 2012-08-02
676 | 2012-08-03
677 | 2012-08-06
678 | 2012-08-07
679 | 2012-08-08
680 | 2012-08-09
681 | 2012-08-10
682 | 2012-08-13
683 | 2012-08-14
684 | 2012-08-15
685 | 2012-08-16
686 | 2012-08-17
687 | 2012-08-20
688 | 2012-08-21
689 | 2012-08-22
690 | 2012-08-23
691 | 2012-08-24
692 | 2012-08-27
693 | 2012-08-28
694 | 2012-08-29
695 | 2012-08-30
696 | 2012-08-31
697 | 2012-09-03
698 | 2012-09-04
699 | 2012-09-05
700 | 2012-09-06
701 | 2012-09-07
702 | 2012-09-10
703 | 2012-09-11
704 | 2012-09-12
705 | 2012-09-13
706 | 2012-09-14
707 | 2012-09-17
708 | 2012-09-18
709 | 2012-09-19
710 | 2012-09-20
711 | 2012-09-21
712 | 2012-09-24
713 | 2012-09-25
714 | 2012-09-26
715 | 2012-09-27
716 | 2012-09-28
717 | 2012-10-01
718 | 2012-10-02
719 | 2012-10-03
720 | 2012-10-04
721 | 2012-10-05
722 | 2012-10-08
723 | 2012-10-09
724 | 2012-10-10
725 | 2012-10-11
726 | 2012-10-12
727 | 2012-10-15
728 | 2012-10-16
729 | 2012-10-17
730 | 2012-10-18
731 | 2012-10-19
732 | 2012-10-22
733 | 2012-10-23
734 | 2012-10-24
735 | 2012-10-25
736 | 2012-10-26
737 | 2012-10-29
738 | 2012-10-30
739 | 2012-10-31
740 | 2012-11-01
741 | 2012-11-02
742 | 2012-11-05
743 | 2012-11-06
744 | 2012-11-07
745 | 2012-11-08
746 | 2012-11-09
747 | 2012-11-12
748 | 2012-11-13
749 | 2012-11-14
750 | 2012-11-15
751 | 2012-11-16
752 | 2012-11-19
753 | 2012-11-20
754 | 2012-11-21
755 | 2012-11-22
756 | 2012-11-23
757 | 2012-11-26
758 | 2012-11-27
759 | 2012-11-28
760 | 2012-11-29
761 | 2012-11-30
762 | 2012-12-03
763 | 2012-12-04
764 | 2012-12-05
765 | 2012-12-06
766 | 2012-12-07
767 | 2012-12-10
768 | 2012-12-11
769 | 2012-12-12
770 | 2012-12-13
771 | 2012-12-14
772 | 2012-12-17
773 | 2012-12-18
774 | 2012-12-19
775 | 2012-12-20
776 | 2012-12-21
777 | 2012-12-24
778 | 2012-12-25
779 | 2012-12-26
780 | 2012-12-27
781 | 2012-12-28
782 | 2012-12-31
783 | 2013-01-01
784 | 2013-01-02
785 | 2013-01-03
786 | 2013-01-04
787 | 2013-01-07
788 | 2013-01-08
789 | 2013-01-09
790 | 2013-01-10
791 | 2013-01-11
792 | 2013-01-14
793 | 2013-01-15
794 | 2013-01-16
795 | 2013-01-17
796 | 2013-01-18
797 | 2013-01-21
798 | 2013-01-22
799 | 2013-01-23
800 | 2013-01-24
801 | 2013-01-25
802 | 2013-01-28
803 | 2013-01-29
804 | 2013-01-30
805 | 2013-01-31
806 | 2013-02-01
807 | 2013-02-04
808 | 2013-02-05
809 | 2013-02-06
810 | 2013-02-07
811 | 2013-02-08
812 | 2013-02-11
813 | 2013-02-12
814 | 2013-02-13
815 | 2013-02-14
816 | 2013-02-15
817 | 2013-02-18
818 | 2013-02-19
819 | 2013-02-20
820 | 2013-02-21
821 | 2013-02-22
822 | 2013-02-25
823 | 2013-02-26
824 | 2013-02-27
825 | 2013-02-28
826 | 2013-03-01
827 | 2013-03-04
828 | 2013-03-05
829 | 2013-03-06
830 | 2013-03-07
831 | 2013-03-08
832 | 2013-03-11
833 | 2013-03-12
834 | 2013-03-13
835 | 2013-03-14
836 | 2013-03-15
837 | 2013-03-18
838 | 2013-03-19
839 | 2013-03-20
840 | 2013-03-21
841 | 2013-03-22
842 | 2013-03-25
843 | 2013-03-26
844 | 2013-03-27
845 | 2013-03-28
846 | 2013-03-29
847 | 2013-04-01
848 | 2013-04-02
849 | 2013-04-03
850 | 2013-04-04
851 | 2013-04-05
852 | 2013-04-08
853 | 2013-04-09
854 | 2013-04-10
855 | 2013-04-11
856 | 2013-04-12
857 | 2013-04-15
858 | 2013-04-16
859 | 2013-04-17
860 | 2013-04-18
861 | 2013-04-19
862 | 2013-04-22
863 | 2013-04-23
864 | 2013-04-24
865 | 2013-04-25
866 | 2013-04-26
867 | 2013-04-29
868 | 2013-04-30
869 | 2013-05-01
870 | 2013-05-02
871 | 2013-05-03
872 | 2013-05-06
873 | 2013-05-07
874 | 2013-05-08
875 | 2013-05-09
876 | 2013-05-10
877 | 2013-05-13
878 | 2013-05-14
879 | 2013-05-15
880 | 2013-05-16
881 | 2013-05-17
882 | 2013-05-20
883 | 2013-05-21
884 | 2013-05-22
885 | 2013-05-23
886 | 2013-05-24
887 | 2013-05-27
888 | 2013-05-28
889 | 2013-05-29
890 | 2013-05-30
891 | 2013-05-31
892 | 2013-06-03
893 | 2013-06-04
894 | 2013-06-05
895 | 2013-06-06
896 | 2013-06-07
897 | 2013-06-10
898 | 2013-06-11
899 | 2013-06-12
900 | 2013-06-13
901 | 2013-06-14
902 | 2013-06-17
903 | 2013-06-18
904 | 2013-06-19
905 | 2013-06-20
906 | 2013-06-21
907 | 2013-06-24
908 | 2013-06-25
909 | 2013-06-26
910 | 2013-06-27
911 | 2013-06-28
912 | 2013-07-01
913 | 2013-07-02
914 | 2013-07-03
915 | 2013-07-04
916 | 2013-07-05
917 | 2013-07-08
918 | 2013-07-09
919 | 2013-07-10
920 | 2013-07-11
921 | 2013-07-12
922 | 2013-07-15
923 | 2013-07-16
924 | 2013-07-17
925 | 2013-07-18
926 | 2013-07-19
927 | 2013-07-22
928 | 2013-07-23
929 | 2013-07-24
930 | 2013-07-25
931 | 2013-07-26
932 | 2013-07-29
933 | 2013-07-30
934 | 2013-07-31
935 | 2013-08-01
936 | 2013-08-02
937 | 2013-08-05
938 | 2013-08-06
939 | 2013-08-07
940 | 2013-08-08
941 | 2013-08-09
942 | 2013-08-12
943 | 2013-08-13
944 | 2013-08-14
945 | 2013-08-15
946 | 2013-08-16
947 | 2013-08-19
948 | 2013-08-20
949 | 2013-08-21
950 | 2013-08-22
951 | 2013-08-23
952 | 2013-08-26
953 | 2013-08-27
954 | 2013-08-28
955 | 2013-08-29
956 | 2013-08-30
957 | 2013-09-02
958 | 2013-09-03
959 | 2013-09-04
960 | 2013-09-05
961 | 2013-09-06
962 | 2013-09-09
963 | 2013-09-10
964 | 2013-09-11
965 | 2013-09-12
966 | 2013-09-13
967 | 2013-09-16
968 | 2013-09-17
969 | 2013-09-18
970 | 2013-09-19
971 | 2013-09-20
972 | 2013-09-23
973 | 2013-09-24
974 | 2013-09-25
975 | 2013-09-26
976 | 2013-09-27
977 | 2013-09-30
978 | 2013-10-01
979 | 2013-10-02
980 | 2013-10-03
981 | 2013-10-04
982 | 2013-10-07
983 | 2013-10-08
984 | 2013-10-09
985 | 2013-10-10
986 | 2013-10-11
987 | 2013-10-14
988 | 2013-10-15
989 | 2013-10-16
990 | 2013-10-17
991 | 2013-10-18
992 | 2013-10-21
993 | 2013-10-22
994 | 2013-10-23
995 | 2013-10-24
996 | 2013-10-25
997 | 2013-10-28
998 | 2013-10-29
999 | 2013-10-30
1000 | 2013-10-31
1001 | 2013-11-01
1002 | 2013-11-04
1003 | 2013-11-05
1004 | 2013-11-06
1005 | 2013-11-07
1006 | 2013-11-08
1007 | 2013-11-11
1008 | 2013-11-12
1009 | 2013-11-13
1010 | 2013-11-14
1011 | 2013-11-15
1012 | 2013-11-18
1013 | 2013-11-19
1014 | 2013-11-20
1015 | 2013-11-21
1016 | 2013-11-22
1017 | 2013-11-25
1018 | 2013-11-26
1019 | 2013-11-27
1020 | 2013-11-28
1021 | 2013-11-29
1022 | 2013-12-02
1023 | 2013-12-03
1024 | 2013-12-04
1025 | 2013-12-05
1026 | 2013-12-06
1027 | 2013-12-09
1028 | 2013-12-10
1029 | 2013-12-11
1030 | 2013-12-12
1031 | 2013-12-13
1032 | 2013-12-16
1033 | 2013-12-17
1034 | 2013-12-18
1035 | 2013-12-19
1036 | 2013-12-20
1037 | 2013-12-23
1038 | 2013-12-24
1039 | 2013-12-25
1040 | 2013-12-26
1041 | 2013-12-27
1042 | 2013-12-30
1043 | 2013-12-31
1044 | 2014-01-01
1045 | 2014-01-02
1046 | 2014-01-03
1047 | 2014-01-06
1048 | 2014-01-07
1049 | 2014-01-08
1050 | 2014-01-09
1051 | 2014-01-10
1052 | 2014-01-13
1053 | 2014-01-14
1054 | 2014-01-15
1055 | 2014-01-16
1056 | 2014-01-17
1057 | 2014-01-20
1058 | 2014-01-21
1059 | 2014-01-22
1060 | 2014-01-23
1061 | 2014-01-24
1062 | 2014-01-27
1063 | 2014-01-28
1064 | 2014-01-29
1065 | 2014-01-30
1066 | 2014-01-31
1067 | 2014-02-03
1068 | 2014-02-04
1069 | 2014-02-05
1070 | 2014-02-06
1071 | 2014-02-07
1072 | 2014-02-10
1073 | 2014-02-11
1074 | 2014-02-12
1075 | 2014-02-13
1076 | 2014-02-14
1077 | 2014-02-17
1078 | 2014-02-18
1079 | 2014-02-19
1080 | 2014-02-20
1081 | 2014-02-21
1082 | 2014-02-24
1083 | 2014-02-25
1084 | 2014-02-26
1085 | 2014-02-27
1086 | 2014-02-28
1087 | 2014-03-03
1088 | 2014-03-04
1089 | 2014-03-05
1090 | 2014-03-06
1091 | 2014-03-07
1092 | 2014-03-10
1093 | 2014-03-11
1094 | 2014-03-12
1095 | 2014-03-13
1096 | 2014-03-14
1097 | 2014-03-17
1098 | 2014-03-18
1099 | 2014-03-19
1100 | 2014-03-20
1101 | 2014-03-21
1102 | 2014-03-24
1103 | 2014-03-25
1104 | 2014-03-26
1105 | 2014-03-27
1106 | 2014-03-28
1107 | 2014-03-31
1108 | 2014-04-01
1109 | 2014-04-02
1110 | 2014-04-03
1111 | 2014-04-04
1112 | 2014-04-07
1113 | 2014-04-08
1114 | 2014-04-09
1115 | 2014-04-10
1116 | 2014-04-11
1117 | 2014-04-14
1118 | 2014-04-15
1119 | 2014-04-16
1120 | 2014-04-17
1121 | 2014-04-18
1122 | 2014-04-21
1123 | 2014-04-22
1124 | 2014-04-23
1125 | 2014-04-24
1126 | 2014-04-25
1127 | 2014-04-28
1128 | 2014-04-29
1129 | 2014-04-30
1130 | 2014-05-01
1131 | 2014-05-02
1132 | 2014-05-05
1133 | 2014-05-06
1134 | 2014-05-07
1135 | 2014-05-08
1136 | 2014-05-09
1137 | 2014-05-12
1138 | 2014-05-13
1139 | 2014-05-14
1140 | 2014-05-15
1141 | 2014-05-16
1142 | 2014-05-19
1143 | 2014-05-20
1144 | 2014-05-21
1145 | 2014-05-22
1146 | 2014-05-23
1147 | 2014-05-26
1148 | 2014-05-27
1149 | 2014-05-28
1150 | 2014-05-29
1151 | 2014-05-30
1152 | 2014-06-02
1153 | 2014-06-03
1154 | 2014-06-04
1155 | 2014-06-05
1156 | 2014-06-06
1157 | 2014-06-09
1158 | 2014-06-10
1159 | 2014-06-11
1160 | 2014-06-12
1161 | 2014-06-13
1162 | 2014-06-16
1163 | 2014-06-17
1164 | 2014-06-18
1165 | 2014-06-19
1166 | 2014-06-20
1167 | 2014-06-23
1168 | 2014-06-24
1169 | 2014-06-25
1170 | 2014-06-26
1171 | 2014-06-27
1172 | 2014-06-30
1173 | 2014-07-01
1174 | 2014-07-02
1175 | 2014-07-03
1176 | 2014-07-04
1177 | 2014-07-07
1178 | 2014-07-08
1179 | 2014-07-09
1180 | 2014-07-10
1181 | 2014-07-11
1182 | 2014-07-14
1183 | 2014-07-15
1184 | 2014-07-16
1185 | 2014-07-17
1186 | 2014-07-18
1187 | 2014-07-21
1188 | 2014-07-22
1189 | 2014-07-23
1190 | 2014-07-24
1191 | 2014-07-25
1192 | 2014-07-28
1193 | 2014-07-29
1194 | 2014-07-30
1195 | 2014-07-31
1196 | 2014-08-01
1197 | 2014-08-04
1198 | 2014-08-05
1199 | 2014-08-06
1200 | 2014-08-07
1201 | 2014-08-08
1202 | 2014-08-11
1203 | 2014-08-12
1204 | 2014-08-13
1205 | 2014-08-14
1206 | 2014-08-15
1207 | 2014-08-18
1208 | 2014-08-19
1209 | 2014-08-20
1210 | 2014-08-21
1211 | 2014-08-22
1212 | 2014-08-25
1213 | 2014-08-26
1214 | 2014-08-27
1215 | 2014-08-28
1216 | 2014-08-29
1217 | 2014-09-01
1218 | 2014-09-02
1219 | 2014-09-03
1220 | 2014-09-04
1221 | 2014-09-05
1222 | 2014-09-08
1223 | 2014-09-09
1224 | 2014-09-10
1225 | 2014-09-11
1226 | 2014-09-12
1227 | 2014-09-15
1228 | 2014-09-16
1229 | 2014-09-17
1230 | 2014-09-18
1231 | 2014-09-19
1232 | 2014-09-22
1233 | 2014-09-23
1234 | 2014-09-24
1235 | 2014-09-25
1236 | 2014-09-26
1237 | 2014-09-29
1238 | 2014-09-30
1239 | 2014-10-01
1240 | 2014-10-02
1241 | 2014-10-03
1242 | 2014-10-06
1243 | 2014-10-07
1244 | 2014-10-08
1245 | 2014-10-09
1246 | 2014-10-10
1247 | 2014-10-13
1248 | 2014-10-14
1249 | 2014-10-15
1250 | 2014-10-16
1251 | 2014-10-17
1252 | 2014-10-20
1253 | 2014-10-21
1254 | 2014-10-22
1255 | 2014-10-23
1256 | 2014-10-24
1257 | 2014-10-27
1258 | 2014-10-28
1259 | 2014-10-29
1260 | 2014-10-30
1261 | 2014-10-31
1262 | 2014-11-03
1263 | 2014-11-04
1264 | 2014-11-05
1265 | 2014-11-06
1266 | 2014-11-07
1267 | 2014-11-10
1268 | 2014-11-11
1269 | 2014-11-12
1270 | 2014-11-13
1271 | 2014-11-14
1272 | 2014-11-17
1273 | 2014-11-18
1274 | 2014-11-19
1275 | 2014-11-20
1276 | 2014-11-21
1277 | 2014-11-24
1278 | 2014-11-25
1279 | 2014-11-26
1280 | 2014-11-27
1281 | 2014-11-28
1282 | 2014-12-01
1283 | 2014-12-02
1284 | 2014-12-03
1285 | 2014-12-04
1286 | 2014-12-05
1287 | 2014-12-08
1288 | 2014-12-09
1289 | 2014-12-10
1290 | 2014-12-11
1291 | 2014-12-12
1292 | 2014-12-15
1293 | 2014-12-16
1294 | 2014-12-17
1295 | 2014-12-18
1296 | 2014-12-19
1297 | 2014-12-22
1298 | 2014-12-23
1299 | 2014-12-24
1300 | 2014-12-25
1301 | 2014-12-26
1302 | 2014-12-29
1303 | 2014-12-30
1304 | 2014-12-31
1305 | 2015-01-01
1306 | 2015-01-02
1307 | 2015-01-05
1308 | 2015-01-06
1309 | 2015-01-07
1310 | 2015-01-08
1311 | 2015-01-09
1312 | 2015-01-12
1313 | 2015-01-13
1314 | 2015-01-14
1315 | 2015-01-15
1316 | 2015-01-16
1317 | 2015-01-19
1318 | 2015-01-20
1319 | 2015-01-21
1320 | 2015-01-22
1321 | 2015-01-23
1322 | 2015-01-26
1323 | 2015-01-27
1324 | 2015-01-28
1325 | 2015-01-29
1326 | 2015-01-30
1327 | 2015-02-02
1328 | 2015-02-03
1329 | 2015-02-04
1330 | 2015-02-05
1331 | 2015-02-06
1332 | 2015-02-09
1333 | 2015-02-10
1334 | 2015-02-11
1335 | 2015-02-12
1336 | 2015-02-13
1337 | 2015-02-16
1338 | 2015-02-17
1339 | 2015-02-18
1340 | 2015-02-19
1341 | 2015-02-20
1342 | 2015-02-23
1343 | 2015-02-24
1344 | 2015-02-25
1345 | 2015-02-26
1346 | 2015-02-27
1347 | 2015-03-02
1348 | 2015-03-03
1349 | 2015-03-04
1350 | 2015-03-05
1351 | 2015-03-06
1352 | 2015-03-09
1353 | 2015-03-10
1354 | 2015-03-11
1355 | 2015-03-12
1356 | 2015-03-13
1357 | 2015-03-16
1358 | 2015-03-17
1359 | 2015-03-18
1360 | 2015-03-19
1361 | 2015-03-20
1362 | 2015-03-23
1363 | 2015-03-24
1364 | 2015-03-25
1365 | 2015-03-26
1366 | 2015-03-27
1367 | 2015-03-30
1368 | 2015-03-31
1369 | 2015-04-01
1370 | 2015-04-02
1371 | 2015-04-03
1372 | 2015-04-06
1373 | 2015-04-07
1374 | 2015-04-08
1375 | 2015-04-09
1376 | 2015-04-10
1377 | 2015-04-13
1378 | 2015-04-14
1379 | 2015-04-15
1380 | 2015-04-16
1381 | 2015-04-17
1382 | 2015-04-20
1383 | 2015-04-21
1384 | 2015-04-22
1385 | 2015-04-23
1386 | 2015-04-24
1387 | 2015-04-27
1388 | 2015-04-28
1389 | 2015-04-29
1390 | 2015-04-30
1391 | 2015-05-01
1392 | 2015-05-04
1393 | 2015-05-05
1394 | 2015-05-06
1395 | 2015-05-07
1396 | 2015-05-08
1397 | 2015-05-11
1398 | 2015-05-12
1399 | 2015-05-13
1400 | 2015-05-14
1401 | 2015-05-15
1402 | 2015-05-18
1403 | 2015-05-19
1404 | 2015-05-20
1405 | 2015-05-21
1406 | 2015-05-22
1407 | 2015-05-25
1408 | 2015-05-26
1409 | 2015-05-27
1410 | 2015-05-28
1411 | 2015-05-29
1412 | 2015-06-01
1413 | 2015-06-02
1414 | 2015-06-03
1415 | 2015-06-04
1416 | 2015-06-05
1417 | 2015-06-08
1418 | 2015-06-09
1419 | 2015-06-10
1420 | 2015-06-11
1421 | 2015-06-12
1422 | 2015-06-15
1423 | 2015-06-16
1424 | 2015-06-17
1425 | 2015-06-18
1426 | 2015-06-19
1427 | 2015-06-22
1428 | 2015-06-23
1429 | 2015-06-24
1430 | 2015-06-25
1431 | 2015-06-26
1432 | 2015-06-29
1433 | 2015-06-30
1434 | 2015-07-01
1435 | 2015-07-02
1436 | 2015-07-03
1437 | 2015-07-06
1438 | 2015-07-07
1439 | 2015-07-08
1440 | 2015-07-09
1441 | 2015-07-10
1442 | 2015-07-13
1443 | 2015-07-14
1444 | 2015-07-15
1445 | 2015-07-16
1446 | 2015-07-17
1447 | 2015-07-20
1448 | 2015-07-21
1449 | 2015-07-22
1450 | 2015-07-23
1451 | 2015-07-24
1452 | 2015-07-27
1453 | 2015-07-28
1454 | 2015-07-29
1455 | 2015-07-30
1456 | 2015-07-31
1457 | 2015-08-03
1458 | 2015-08-04
1459 | 2015-08-05
1460 | 2015-08-06
1461 | 2015-08-07
1462 | 2015-08-10
1463 | 2015-08-11
1464 | 2015-08-12
1465 | 2015-08-13
1466 | 2015-08-14
1467 | 2015-08-17
1468 | 2015-08-18
1469 | 2015-08-19
1470 | 2015-08-20
1471 | 2015-08-21
1472 | 2015-08-24
1473 | 2015-08-25
1474 | 2015-08-26
1475 | 2015-08-27
1476 | 2015-08-28
1477 | 2015-08-31
1478 | 2015-09-01
1479 | 2015-09-02
1480 | 2015-09-03
1481 | 2015-09-04
1482 | 2015-09-07
1483 | 2015-09-08
1484 | 2015-09-09
1485 | 2015-09-10
1486 | 2015-09-11
1487 | 2015-09-14
1488 | 2015-09-15
1489 | 2015-09-16
1490 | 2015-09-17
1491 | 2015-09-18
1492 | 2015-09-21
1493 | 2015-09-22
1494 | 2015-09-23
1495 | 2015-09-24
1496 | 2015-09-25
1497 | 2015-09-28
1498 | 2015-09-29
1499 | 2015-09-30
1500 | 2015-10-01
1501 | 2015-10-02
1502 | 2015-10-05
1503 | 2015-10-06
1504 | 2015-10-07
1505 | 2015-10-08
1506 | 2015-10-09
1507 | 2015-10-12
1508 | 2015-10-13
1509 | 2015-10-14
1510 | 2015-10-15
1511 | 2015-10-16
1512 | 2015-10-19
1513 | 2015-10-20
1514 | 2015-10-21
1515 | 2015-10-22
1516 | 2015-10-23
1517 | 2015-10-26
1518 | 2015-10-27
1519 | 2015-10-28
1520 | 2015-10-29
1521 | 2015-10-30
1522 | 2015-11-02
1523 | 2015-11-03
1524 | 2015-11-04
1525 | 2015-11-05
1526 | 2015-11-06
1527 | 2015-11-09
1528 | 2015-11-10
1529 | 2015-11-11
1530 | 2015-11-12
1531 | 2015-11-13
1532 | 2015-11-16
1533 | 2015-11-17
1534 | 2015-11-18
1535 | 2015-11-19
1536 | 2015-11-20
1537 | 2015-11-23
1538 | 2015-11-24
1539 | 2015-11-25
1540 | 2015-11-26
1541 | 2015-11-27
1542 | 2015-11-30
1543 | 2015-12-01
1544 | 2015-12-02
1545 | 2015-12-03
1546 | 2015-12-04
1547 | 2015-12-07
1548 | 2015-12-08
1549 | 2015-12-09
1550 | 2015-12-10
1551 | 2015-12-11
1552 | 2015-12-14
1553 | 2015-12-15
1554 | 2015-12-16
1555 | 2015-12-17
1556 | 2015-12-18
1557 | 2015-12-21
1558 | 2015-12-22
1559 | 2015-12-23
1560 | 2015-12-24
1561 | 2015-12-25
1562 | 2015-12-28
1563 | 2015-12-29
1564 | 2015-12-30
1565 | 2015-12-31
1566 | 2016-01-01
1567 | 2016-01-04
1568 | 2016-01-05
1569 | 2016-01-06
1570 | 2016-01-07
1571 | 2016-01-08
1572 | 2016-01-11
1573 | 2016-01-12
1574 | 2016-01-13
1575 | 2016-01-14
1576 | 2016-01-15
1577 | 2016-01-18
1578 | 2016-01-19
1579 | 2016-01-20
1580 | 2016-01-21
1581 | 2016-01-22
1582 | 2016-01-25
1583 | 2016-01-26
1584 | 2016-01-27
1585 | 2016-01-28
1586 | 2016-01-29
1587 | 2016-02-01
1588 | 2016-02-02
1589 | 2016-02-03
1590 | 2016-02-04
1591 | 2016-02-05
1592 | 2016-02-08
1593 | 2016-02-09
1594 | 2016-02-10
1595 | 2016-02-11
1596 | 2016-02-12
1597 | 2016-02-15
1598 | 2016-02-16
1599 | 2016-02-17
1600 | 2016-02-18
1601 | 2016-02-19
1602 | 2016-02-22
1603 | 2016-02-23
1604 | 2016-02-24
1605 | 2016-02-25
1606 | 2016-02-26
1607 | 2016-02-29
1608 | 2016-03-01
1609 | 2016-03-02
1610 | 2016-03-03
1611 | 2016-03-04
1612 | 2016-03-07
1613 | 2016-03-08
1614 | 2016-03-09
1615 | 2016-03-10
1616 | 2016-03-11
1617 | 2016-03-14
1618 | 2016-03-15
1619 | 2016-03-16
1620 | 2016-03-17
1621 | 2016-03-18
1622 | 2016-03-21
1623 | 2016-03-22
1624 | 2016-03-23
1625 | 2016-03-24
1626 | 2016-03-25
1627 | 2016-03-28
1628 | 2016-03-29
1629 | 2016-03-30
1630 | 2016-03-31
1631 | 2016-04-01
1632 | 2016-04-04
1633 | 2016-04-05
1634 | 2016-04-06
1635 | 2016-04-07
1636 | 2016-04-08
1637 | 2016-04-11
1638 | 2016-04-12
1639 | 2016-04-13
1640 | 2016-04-14
1641 | 2016-04-15
1642 | 2016-04-18
1643 | 2016-04-19
1644 | 2016-04-20
1645 | 2016-04-21
1646 | 2016-04-22
1647 | 2016-04-25
1648 | 2016-04-26
1649 | 2016-04-27
1650 | 2016-04-28
1651 | 2016-04-29
1652 | 2016-05-02
1653 | 2016-05-03
1654 | 2016-05-04
1655 | 2016-05-05
1656 | 2016-05-06
1657 | 2016-05-09
1658 | 2016-05-10
1659 | 2016-05-11
1660 | 2016-05-12
1661 | 2016-05-13
1662 | 2016-05-16
1663 | 2016-05-17
1664 | 2016-05-18
1665 | 2016-05-19
1666 | 2016-05-20
1667 | 2016-05-23
1668 | 2016-05-24
1669 | 2016-05-25
1670 | 2016-05-26
1671 | 2016-05-27
1672 | 2016-05-30
1673 | 2016-05-31
1674 | 2016-06-01
1675 | 2016-06-02
1676 | 2016-06-03
1677 | 2016-06-06
1678 | 2016-06-07
1679 | 2016-06-08
1680 | 2016-06-09
1681 | 2016-06-10
1682 | 2016-06-13
1683 | 2016-06-14
1684 | 2016-06-15
1685 | 2016-06-16
1686 | 2016-06-17
1687 | 2016-06-20
1688 | 2016-06-21
1689 | 2016-06-22
1690 | 2016-06-23
1691 | 2016-06-24
1692 | 2016-06-27
1693 | 2016-06-28
1694 | 2016-06-29
1695 | 2016-06-30
1696 | 2016-07-01
1697 | 2016-07-04
1698 | 2016-07-05
1699 | 2016-07-06
1700 | 2016-07-07
1701 | 2016-07-08
1702 | 2016-07-11
1703 | 2016-07-12
1704 | 2016-07-13
1705 | 2016-07-14
1706 | 2016-07-15
1707 | 2016-07-18
1708 | 2016-07-19
1709 | 2016-07-20
1710 | 2016-07-21
1711 | 2016-07-22
1712 | 2016-07-25
1713 | 2016-07-26
1714 | 2016-07-27
1715 | 2016-07-28
1716 | 2016-07-29
1717 | 2016-08-01
1718 | 2016-08-02
1719 | 2016-08-03
1720 | 2016-08-04
1721 | 2016-08-05
1722 | 2016-08-08
1723 | 2016-08-09
1724 | 2016-08-10
1725 | 2016-08-11
1726 | 2016-08-12
1727 | 2016-08-15
1728 | 2016-08-16
1729 | 2016-08-17
1730 | 2016-08-18
1731 | 2016-08-19
1732 | 2016-08-22
1733 | 2016-08-23
1734 | 2016-08-24
1735 | 2016-08-25
1736 | 2016-08-26
1737 | 2016-08-29
1738 | 2016-08-30
1739 | 2016-08-31
1740 | 2016-09-01
1741 | 2016-09-02
1742 | 2016-09-05
1743 | 2016-09-06
1744 | 2016-09-07
1745 | 2016-09-08
1746 | 2016-09-09
1747 | 2016-09-12
1748 | 2016-09-13
1749 | 2016-09-14
1750 | 2016-09-15
1751 | 2016-09-16
1752 | 2016-09-19
1753 | 2016-09-20
1754 | 2016-09-21
1755 | 2016-09-22
1756 | 2016-09-23
1757 | 2016-09-26
1758 | 2016-09-27
1759 | 2016-09-28
1760 | 2016-09-29
1761 | 2016-09-30
1762 | 2016-10-03
1763 | 2016-10-04
1764 | 2016-10-05
1765 | 2016-10-06
1766 | 2016-10-07
1767 | 2016-10-10
1768 | 2016-10-11
1769 | 2016-10-12
1770 | 2016-10-13
1771 | 2016-10-14
1772 | 2016-10-17
1773 | 2016-10-18
1774 | 2016-10-19
1775 | 2016-10-20
1776 | 2016-10-21
1777 | 2016-10-24
1778 | 2016-10-25
1779 | 2016-10-26
1780 | 2016-10-27
1781 | 2016-10-28
1782 | 2016-10-31
1783 | 2016-11-01
1784 | 2016-11-02
1785 | 2016-11-03
1786 | 2016-11-04
1787 | 2016-11-07
1788 | 2016-11-08
1789 | 2016-11-09
1790 | 2016-11-10
1791 | 2016-11-11
1792 | 2016-11-14
1793 | 2016-11-15
1794 | 2016-11-16
1795 | 2016-11-17
1796 | 2016-11-18
1797 | 2016-11-21
1798 | 2016-11-22
1799 | 2016-11-23
1800 | 2016-11-24
1801 | 2016-11-25
1802 | 2016-11-28
1803 | 2016-11-29
1804 | 2016-11-30
1805 | 2016-12-01
1806 | 2016-12-02
1807 | 2016-12-05
1808 | 2016-12-06
1809 | 2016-12-07
1810 | 2016-12-08
1811 | 2016-12-09
1812 | 2016-12-12
1813 | 2016-12-13
1814 | 2016-12-14
1815 | 2016-12-15
1816 | 2016-12-16
1817 | 2016-12-19
1818 | 2016-12-20
1819 | 2016-12-21
1820 | 2016-12-22
1821 | 2016-12-23
1822 | 2016-12-26
1823 | 2016-12-27
1824 | 2016-12-28
1825 | 2016-12-29
1826 | 2016-12-30
1827 | 2017-01-02
1828 | 2017-01-03
1829 | 2017-01-04
1830 | 2017-01-05
1831 | 2017-01-06
1832 | 2017-01-09
1833 | 2017-01-10
1834 | 2017-01-11
1835 | 2017-01-12
1836 | 2017-01-13
1837 | 2017-01-16
1838 | 2017-01-17
1839 | 2017-01-18
1840 | 2017-01-19
1841 | 2017-01-20
1842 | 2017-01-23
1843 | 2017-01-24
1844 | 2017-01-25
1845 | 2017-01-26
1846 | 2017-01-27
1847 | 2017-01-30
1848 | 2017-01-31
1849 | 2017-02-01
1850 | 2017-02-02
1851 | 2017-02-03
1852 | 2017-02-06
1853 | 2017-02-07
1854 | 2017-02-08
1855 | 2017-02-09
1856 | 2017-02-10
1857 | 2017-02-13
1858 | 2017-02-14
1859 | 2017-02-15
1860 | 2017-02-16
1861 | 2017-02-17
1862 | 2017-02-20
1863 | 2017-02-21
1864 | 2017-02-22
1865 | 2017-02-23
1866 | 2017-02-24
1867 | 2017-02-27
1868 | 2017-02-28
1869 | 2017-03-01
1870 | 2017-03-02
1871 | 2017-03-03
1872 | 2017-03-06
1873 | 2017-03-07
1874 | 2017-03-08
1875 | 2017-03-09
1876 | 2017-03-10
1877 | 2017-03-13
1878 | 2017-03-14
1879 | 2017-03-15
1880 | 2017-03-16
1881 | 2017-03-17
1882 | 2017-03-20
1883 | 2017-03-21
1884 | 2017-03-22
1885 | 2017-03-23
1886 | 2017-03-24
1887 | 2017-03-27
1888 | 2017-03-28
1889 | 2017-03-29
1890 | 2017-03-30
1891 | 2017-03-31
1892 | 2017-04-03
1893 | 2017-04-04
1894 | 2017-04-05
1895 | 2017-04-06
1896 | 2017-04-07
1897 | 2017-04-10
1898 | 2017-04-11
1899 | 2017-04-12
1900 | 2017-04-13
1901 | 2017-04-14
1902 | 2017-04-17
1903 | 2017-04-18
1904 | 2017-04-19
1905 | 2017-04-20
1906 | 2017-04-21
1907 | 2017-04-24
1908 | 2017-04-25
1909 | 2017-04-26
1910 | 2017-04-27
1911 | 2017-04-28
1912 | 2017-05-01
1913 | 2017-05-02
1914 | 2017-05-03
1915 | 2017-05-04
1916 | 2017-05-05
1917 | 2017-05-08
1918 | 2017-05-09
1919 | 2017-05-10
1920 | 2017-05-11
1921 | 2017-05-12
1922 | 2017-05-15
1923 | 2017-05-16
1924 | 2017-05-17
1925 | 2017-05-18
1926 | 2017-05-19
1927 | 2017-05-22
1928 | 2017-05-23
1929 | 2017-05-24
1930 | 2017-05-25
1931 | 2017-05-26
1932 | 2017-05-29
1933 | 2017-05-30
1934 | 2017-05-31
1935 | 2017-06-01
1936 | 2017-06-02
1937 | 2017-06-05
1938 | 2017-06-06
1939 | 2017-06-07
1940 | 2017-06-08
1941 | 2017-06-09
1942 | 2017-06-12
1943 | 2017-06-13
1944 | 2017-06-14
1945 | 2017-06-15
1946 | 2017-06-16
1947 | 2017-06-19
1948 | 2017-06-20
1949 | 2017-06-21
1950 | 2017-06-22
1951 | 2017-06-23
1952 | 2017-06-26
1953 | 2017-06-27
1954 | 2017-06-28
1955 | 2017-06-29
1956 | 2017-06-30
1957 | 2017-07-03
1958 | 2017-07-04
1959 | 2017-07-05
1960 | 2017-07-06
1961 | 2017-07-07
1962 | 2017-07-10
1963 | 2017-07-11
1964 | 2017-07-12
1965 | 2017-07-13
1966 | 2017-07-14
1967 | 2017-07-17
1968 | 2017-07-18
1969 | 2017-07-19
1970 | 2017-07-20
1971 | 2017-07-21
1972 | 2017-07-24
1973 | 2017-07-25
1974 | 2017-07-26
1975 | 2017-07-27
1976 | 2017-07-28
1977 | 2017-07-31
1978 | 2017-08-01
1979 | 2017-08-02
1980 | 2017-08-03
1981 | 2017-08-04
1982 | 2017-08-07
1983 | 2017-08-08
1984 | 2017-08-09
1985 | 2017-08-10
1986 | 2017-08-11
1987 | 2017-08-14
1988 | 2017-08-15
1989 | 2017-08-16
1990 | 2017-08-17
1991 | 2017-08-18
1992 | 2017-08-21
1993 | 2017-08-22
1994 | 2017-08-23
1995 | 2017-08-24
1996 | 2017-08-25
1997 | 2017-08-28
1998 | 2017-08-29
1999 | 2017-08-30
2000 | 2017-08-31
2001 | 2017-09-01
2002 | 2017-09-04
2003 | 2017-09-05
2004 | 2017-09-06
2005 | 2017-09-07
2006 | 2017-09-08
2007 | 2017-09-11
2008 | 2017-09-12
2009 | 2017-09-13
2010 | 2017-09-14
2011 | 2017-09-15
2012 | 2017-09-18
2013 | 2017-09-19
2014 | 2017-09-20
2015 | 2017-09-21
2016 | 2017-09-22
2017 | 2017-09-25
2018 | 2017-09-26
2019 | 2017-09-27
2020 | 2017-09-28
2021 | 2017-09-29
2022 | 2017-10-02
2023 | 2017-10-03
2024 | 2017-10-04
2025 | 2017-10-05
2026 | 2017-10-06
2027 | 2017-10-09
2028 | 2017-10-10
2029 | 2017-10-11
2030 | 2017-10-12
2031 | 2017-10-13
2032 | 2017-10-16
2033 | 2017-10-17
2034 | 2017-10-18
2035 | 2017-10-19
2036 | 2017-10-20
2037 | 2017-10-23
2038 | 2017-10-24
2039 | 2017-10-25
2040 | 2017-10-26
2041 | 2017-10-27
2042 | 2017-10-30
2043 | 2017-10-31
2044 | 2017-11-01
2045 | 2017-11-02
2046 | 2017-11-03
2047 | 2017-11-06
2048 | 2017-11-07
2049 | 2017-11-08
2050 | 2017-11-09
2051 | 2017-11-10
2052 | 2017-11-13
2053 | 2017-11-14
2054 | 2017-11-15
2055 | 2017-11-16
2056 | 2017-11-17
2057 | 2017-11-20
2058 | 2017-11-21
2059 | 2017-11-22
2060 | 2017-11-23
2061 | 2017-11-24
2062 | 2017-11-27
2063 | 2017-11-28
2064 | 2017-11-29
2065 | 2017-11-30
2066 | 2017-12-01
2067 | 2017-12-04
2068 | 2017-12-05
2069 | 2017-12-06
2070 | 2017-12-07
2071 | 2017-12-08
2072 | 2017-12-11
2073 | 2017-12-12
2074 | 2017-12-13
2075 | 2017-12-14
2076 | 2017-12-15
2077 | 2017-12-18
2078 | 2017-12-19
2079 | 2017-12-20
2080 | 2017-12-21
2081 | 2017-12-22
2082 | 2017-12-25
2083 | 2017-12-26
2084 | 2017-12-27
2085 | 2017-12-28
2086 | 2017-12-29
2087 | 2018-01-01
2088 | 2018-01-02
2089 | 2018-01-03
2090 | 2018-01-04
2091 | 2018-01-05
2092 | 2018-01-08
2093 | 2018-01-09
2094 | 2018-01-10
2095 | 2018-01-11
2096 | 2018-01-12
2097 | 2018-01-15
2098 | 2018-01-16
2099 | 2018-01-17
2100 | 2018-01-18
2101 | 2018-01-19
2102 | 2018-01-22
2103 | 2018-01-23
2104 | 2018-01-24
2105 | 2018-01-25
2106 | 2018-01-26
2107 | 2018-01-29
2108 | 2018-01-30
2109 | 2018-01-31
2110 | 2018-02-01
2111 | 2018-02-02
2112 | 2018-02-05
2113 | 2018-02-06
2114 | 2018-02-07
2115 | 2018-02-08
2116 | 2018-02-09
2117 | 2018-02-12
2118 | 2018-02-13
2119 | 2018-02-14
2120 | 2018-02-15
2121 | 2018-02-16
2122 | 2018-02-19
2123 | 2018-02-20
2124 | 2018-02-21
2125 | 2018-02-22
2126 | 2018-02-23
2127 | 2018-02-26
2128 | 2018-02-27
2129 | 2018-02-28
2130 | 2018-03-01
2131 | 2018-03-02
2132 | 2018-03-05
2133 | 2018-03-06
2134 | 2018-03-07
2135 | 2018-03-08
2136 | 2018-03-09
2137 | 2018-03-12
2138 | 2018-03-13
2139 | 2018-03-14
2140 | 2018-03-15
2141 | 2018-03-16
2142 | 2018-03-19
2143 | 2018-03-20
2144 | 2018-03-21
2145 | 2018-03-22
2146 | 2018-03-23
2147 | 2018-03-26
2148 | 2018-03-27
2149 | 2018-03-28
2150 | 2018-03-29
2151 | 2018-03-30
2152 | 2018-04-02
2153 | 2018-04-03
2154 | 2018-04-04
2155 | 2018-04-05
2156 | 2018-04-06
2157 | 2018-04-09
2158 | 2018-04-10
2159 | 2018-04-11
2160 | 2018-04-12
2161 | 2018-04-13
2162 | 2018-04-16
2163 | 2018-04-17
2164 | 2018-04-18
2165 | 2018-04-19
2166 | 2018-04-20
2167 | 2018-04-23
2168 | 2018-04-24
2169 | 2018-04-25
2170 | 2018-04-26
2171 | 2018-04-27
2172 | 2018-04-30
2173 | 2018-05-01
2174 | 2018-05-02
2175 | 2018-05-03
2176 | 2018-05-04
2177 | 2018-05-07
2178 | 2018-05-08
2179 | 2018-05-09
2180 | 2018-05-10
2181 | 2018-05-11
2182 | 2018-05-14
2183 | 2018-05-15
2184 | 2018-05-16
2185 | 2018-05-17
2186 | 2018-05-18
2187 | 2018-05-21
2188 | 2018-05-22
2189 | 2018-05-23
2190 | 2018-05-24
2191 | 2018-05-25
2192 | 2018-05-28
2193 | 2018-05-29
2194 | 2018-05-30
2195 | 2018-05-31
2196 | 2018-06-01
2197 | 2018-06-04
2198 | 2018-06-05
2199 | 2018-06-06
2200 | 2018-06-07
2201 | 2018-06-08
2202 | 2018-06-11
2203 | 2018-06-12
2204 | 2018-06-13
2205 | 2018-06-14
2206 | 2018-06-15
2207 | 2018-06-18
2208 | 2018-06-19
2209 | 2018-06-20
2210 | 2018-06-21
2211 | 2018-06-22
2212 | 2018-06-25
2213 | 2018-06-26
2214 | 2018-06-27
2215 | 2018-06-28
2216 | 2018-06-29
2217 | 2018-07-02
2218 | 2018-07-03
2219 | 2018-07-04
2220 | 2018-07-05
2221 | 2018-07-06
2222 | 2018-07-09
2223 | 2018-07-10
2224 | 2018-07-11
2225 | 2018-07-12
2226 | 2018-07-13
2227 | 2018-07-16
2228 | 2018-07-17
2229 | 2018-07-18
2230 | 2018-07-19
2231 | 2018-07-20
2232 | 2018-07-23
2233 | 2018-07-24
2234 | 2018-07-25
2235 | 2018-07-26
2236 | 2018-07-27
2237 | 2018-07-30
2238 | 2018-07-31
2239 | 2018-08-01
2240 | 2018-08-02
2241 | 2018-08-03
2242 | 2018-08-06
2243 | 2018-08-07
2244 | 2018-08-08
2245 | 2018-08-09
2246 | 2018-08-10
2247 | 2018-08-13
2248 | 2018-08-14
2249 | 2018-08-15
2250 | 2018-08-16
2251 | 2018-08-17
2252 | 2018-08-20
2253 | 2018-08-21
2254 | 2018-08-22
2255 | 2018-08-23
2256 | 2018-08-24
2257 | 2018-08-27
2258 | 2018-08-28
2259 | 2018-08-29
2260 | 2018-08-30
2261 | 2018-08-31
2262 | 2018-09-03
2263 | 2018-09-04
2264 | 2018-09-05
2265 | 2018-09-06
2266 | 2018-09-07
2267 | 2018-09-10
2268 | 2018-09-11
2269 | 2018-09-12
2270 | 2018-09-13
2271 | 2018-09-14
2272 | 2018-09-17
2273 | 2018-09-18
2274 | 2018-09-19
2275 | 2018-09-20
2276 | 2018-09-21
2277 | 2018-09-24
2278 | 2018-09-25
2279 | 2018-09-26
2280 | 2018-09-27
2281 | 2018-09-28
2282 | 2018-10-01
2283 | 2018-10-02
2284 | 2018-10-03
2285 | 2018-10-04
2286 | 2018-10-05
2287 | 2018-10-08
2288 | 2018-10-09
2289 | 2018-10-10
2290 | 2018-10-11
2291 | 2018-10-12
2292 | 2018-10-15
2293 | 2018-10-16
2294 | 2018-10-17
2295 | 2018-10-18
2296 | 2018-10-19
2297 | 2018-10-22
2298 | 2018-10-23
2299 | 2018-10-24
2300 | 2018-10-25
2301 | 2018-10-26
2302 | 2018-10-29
2303 | 2018-10-30
2304 | 2018-10-31
2305 | 2018-11-01
2306 | 2018-11-02
2307 | 2018-11-05
2308 | 2018-11-06
2309 | 2018-11-07
2310 | 2018-11-08
2311 | 2018-11-09
2312 | 2018-11-12
2313 | 2018-11-13
2314 | 2018-11-14
2315 | 2018-11-15
2316 | 2018-11-16
2317 | 2018-11-19
2318 | 2018-11-20
2319 | 2018-11-21
2320 | 2018-11-22
2321 | 2018-11-23
2322 | 2018-11-26
2323 | 2018-11-27
2324 | 2018-11-28
2325 | 2018-11-29
2326 | 2018-11-30
2327 | 2018-12-03
2328 | 2018-12-04
2329 | 2018-12-05
2330 | 2018-12-06
2331 | 2018-12-07
2332 | 2018-12-10
2333 | 2018-12-11
2334 | 2018-12-12
2335 | 2018-12-13
2336 | 2018-12-14
2337 | 2018-12-17
2338 | 2018-12-18
2339 | 2018-12-19
2340 | 2018-12-20
2341 | 2018-12-21
2342 | 2018-12-24
2343 | 2018-12-25
2344 | 2018-12-26
2345 | 2018-12-27
2346 | 2018-12-28
2347 | 2018-12-31
2348 | 2019-01-01
2349 | 2019-01-02
2350 | 2019-01-03
2351 | 2019-01-04
2352 | 2019-01-07
2353 | 2019-01-08
2354 | 2019-01-09
2355 | 2019-01-10
2356 | 2019-01-11
2357 | 2019-01-14
2358 | 2019-01-15
2359 | 2019-01-16
2360 | 2019-01-17
2361 | 2019-01-18
2362 | 2019-01-21
2363 | 2019-01-22
2364 | 2019-01-23
2365 | 2019-01-24
2366 | 2019-01-25
2367 | 2019-01-28
2368 | 2019-01-29
2369 | 2019-01-30
2370 | 2019-01-31
2371 | 2019-02-01
2372 | 2019-02-04
2373 | 2019-02-05
2374 | 2019-02-06
2375 | 2019-02-07
2376 | 2019-02-08
2377 | 2019-02-11
2378 | 2019-02-12
2379 | 2019-02-13
2380 | 2019-02-14
2381 | 2019-02-15
2382 | 2019-02-18
2383 | 2019-02-19
2384 | 2019-02-20
2385 | 2019-02-21
2386 | 2019-02-22
2387 | 2019-02-25
2388 | 2019-02-26
2389 | 2019-02-27
2390 | 2019-02-28
2391 | 2019-03-01
2392 | 2019-03-04
2393 | 2019-03-05
2394 | 2019-03-06
2395 | 2019-03-07
2396 | 2019-03-08
2397 | 2019-03-11
2398 | 2019-03-12
2399 | 2019-03-13
2400 | 2019-03-14
2401 | 2019-03-15
2402 | 2019-03-18
2403 | 2019-03-19
2404 | 2019-03-20
2405 | 2019-03-21
2406 | 2019-03-22
2407 | 2019-03-25
2408 | 2019-03-26
2409 | 2019-03-27
2410 | 2019-03-28
2411 | 2019-03-29
2412 | 2019-04-01
2413 | 2019-04-02
2414 | 2019-04-03
2415 | 2019-04-04
2416 | 2019-04-05
2417 | 2019-04-08
2418 | 2019-04-09
2419 | 2019-04-10
2420 | 2019-04-11
2421 | 2019-04-12
2422 | 2019-04-15
2423 | 2019-04-16
2424 | 2019-04-17
2425 | 2019-04-18
2426 | 2019-04-19
2427 | 2019-04-22
2428 | 2019-04-23
2429 | 2019-04-24
2430 | 2019-04-25
2431 | 2019-04-26
2432 | 2019-04-29
2433 | 2019-04-30
2434 | 2019-05-01
2435 | 2019-05-02
2436 | 2019-05-03
2437 | 2019-05-06
2438 | 2019-05-07
2439 | 2019-05-08
2440 | 2019-05-09
2441 | 2019-05-10
2442 | 2019-05-13
2443 | 2019-05-14
2444 | 2019-05-15
2445 | 2019-05-16
2446 | 2019-05-17
2447 | 2019-05-20
2448 | 2019-05-21
2449 | 2019-05-22
2450 | 2019-05-23
2451 | 2019-05-24
2452 | 2019-05-27
2453 | 2019-05-28
2454 | 2019-05-29
2455 | 2019-05-30
2456 | 2019-05-31
2457 | 2019-06-03
2458 | 2019-06-04
2459 | 2019-06-05
2460 | 2019-06-06
2461 | 2019-06-07
2462 | 2019-06-10
2463 | 2019-06-11
2464 | 2019-06-12
2465 | 2019-06-13
2466 | 2019-06-14
2467 | 2019-06-17
2468 | 2019-06-18
2469 | 2019-06-19
2470 | 2019-06-20
2471 | 2019-06-21
2472 | 2019-06-24
2473 | 2019-06-25
2474 | 2019-06-26
2475 | 2019-06-27
2476 | 2019-06-28
2477 | 2019-07-01
2478 | 2019-07-02
2479 | 2019-07-03
2480 | 2019-07-04
2481 | 2019-07-05
2482 | 2019-07-08
2483 | 2019-07-09
2484 | 2019-07-10
2485 | 2019-07-11
2486 | 2019-07-12
2487 | 2019-07-15
2488 | 2019-07-16
2489 | 2019-07-17
2490 | 2019-07-18
2491 | 2019-07-19
2492 | 2019-07-22
2493 | 2019-07-23
2494 | 2019-07-24
2495 | 2019-07-25
2496 | 2019-07-26
2497 | 2019-07-29
2498 | 2019-07-30
2499 | 2019-07-31
2500 | 2019-08-01
2501 | 2019-08-02
2502 | 2019-08-05
2503 | 2019-08-06
2504 | 2019-08-07
2505 | 2019-08-08
2506 | 2019-08-09
2507 | 2019-08-12
2508 | 2019-08-13
2509 | 2019-08-14
2510 | 2019-08-15
2511 | 2019-08-16
2512 | 2019-08-19
2513 | 2019-08-20
2514 | 2019-08-21
2515 | 2019-08-22
2516 | 2019-08-23
2517 | 2019-08-26
2518 | 2019-08-27
2519 | 2019-08-28
2520 | 2019-08-29
2521 | 2019-08-30
2522 | 2019-09-02
2523 | 2019-09-03
2524 | 2019-09-04
2525 | 2019-09-05
2526 | 2019-09-06
2527 | 2019-09-09
2528 | 2019-09-10
2529 | 2019-09-11
2530 | 2019-09-12
2531 | 2019-09-13
2532 | 2019-09-16
2533 | 2019-09-17
2534 | 2019-09-18
2535 | 2019-09-19
2536 | 2019-09-20
2537 | 2019-09-23
2538 | 2019-09-24
2539 | 2019-09-25
2540 | 2019-09-26
2541 | 2019-09-27
2542 | 2019-09-30
2543 | 2019-10-01
2544 | 2019-10-02
2545 | 2019-10-03
2546 | 2019-10-04
2547 | 2019-10-07
2548 | 2019-10-08
2549 | 2019-10-09
2550 | 2019-10-10
2551 | 2019-10-11
2552 | 2019-10-14
2553 | 2019-10-15
2554 | 2019-10-16
2555 | 2019-10-17
2556 | 2019-10-18
2557 | 2019-10-21
2558 | 2019-10-22
2559 | 2019-10-23
2560 | 2019-10-24
2561 | 2019-10-25
2562 | 2019-10-28
2563 | 2019-10-29
2564 | 2019-10-30
2565 | 2019-10-31
2566 | 2019-11-01
2567 | 2019-11-04
2568 | 2019-11-05
2569 | 2019-11-06
2570 | 2019-11-07
2571 | 2019-11-08
2572 | 2019-11-11
2573 | 2019-11-12
2574 | 2019-11-13
2575 | 2019-11-14
2576 | 2019-11-15
2577 | 2019-11-18
2578 | 2019-11-19
2579 | 2019-11-20
2580 | 2019-11-21
2581 | 2019-11-22
2582 | 2019-11-25
2583 | 2019-11-26
2584 | 2019-11-27
2585 | 2019-11-28
2586 | 2019-11-29
2587 | 2019-12-02
2588 | 2019-12-03
2589 | 2019-12-04
2590 | 2019-12-05
2591 | 2019-12-06
2592 | 2019-12-09
2593 | 2019-12-10
2594 | 2019-12-11
2595 | 2019-12-12
2596 | 2019-12-13
2597 | 2019-12-16
2598 | 2019-12-17
2599 | 2019-12-18
2600 | 2019-12-19
2601 | 2019-12-20
2602 | 2019-12-23
2603 | 2019-12-24
2604 | 2019-12-25
2605 | 2019-12-26
2606 | 2019-12-27
2607 | 2019-12-30
2608 | 2019-12-31
2609 | 2020-01-01
2610 | 2020-01-02
2611 | 2020-01-03
2612 | 2020-01-06
2613 | 2020-01-07
2614 | 2020-01-08
2615 | 2020-01-09
2616 | 2020-01-10
2617 | 2020-01-13
2618 | 2020-01-14
2619 | 2020-01-15
2620 | 2020-01-16
2621 | 2020-01-17
2622 | 2020-01-20
2623 | 2020-01-21
2624 | 2020-01-22
2625 | 2020-01-23
2626 | 2020-01-24
2627 | 2020-01-27
2628 | 2020-01-28
2629 | 2020-01-29
2630 | 2020-01-30
2631 | 2020-01-31
2632 | 2020-02-03
2633 | 2020-02-04
2634 | 2020-02-05
2635 | 2020-02-06
2636 | 2020-02-07
2637 | 2020-02-10
2638 | 2020-02-11
2639 | 2020-02-12
2640 | 2020-02-13
2641 | 2020-02-14
2642 | 2020-02-17
2643 | 2020-02-18
2644 | 2020-02-19
2645 | 2020-02-20
2646 | 2020-02-21
2647 | 2020-02-24
2648 | 2020-02-25
2649 | 2020-02-26
2650 | 2020-02-27
2651 | 2020-02-28
2652 | 2020-03-02
2653 | 2020-03-03
2654 | 2020-03-04
2655 | 2020-03-05
2656 | 2020-03-06
2657 | 2020-03-09
2658 | 2020-03-10
2659 | 2020-03-11
2660 | 2020-03-12
2661 | 2020-03-13
2662 | 2020-03-16
2663 | 2020-03-17
2664 | 2020-03-18
2665 | 2020-03-19
2666 | 2020-03-20
2667 | 2020-03-23
2668 | 2020-03-24
2669 | 2020-03-25
2670 | 2020-03-26
2671 | 2020-03-27
2672 | 2020-03-30
2673 | 2020-03-31
2674 | 2020-04-01
2675 | 2020-04-02
2676 | 2020-04-03
2677 | 2020-04-06
2678 | 2020-04-07
2679 | 2020-04-08
2680 | 2020-04-09
2681 | 2020-04-10
2682 | 2020-04-13
2683 | 2020-04-14
2684 | 2020-04-15
2685 | 2020-04-16
2686 | 2020-04-17
2687 | 2020-04-20
2688 | 2020-04-21
2689 | 2020-04-22
2690 | 2020-04-23
2691 | 2020-04-24
2692 | 2020-04-27
2693 | 2020-04-28
2694 | 2020-04-29
2695 | 2020-04-30
2696 | 2020-05-01
2697 | 2020-05-04
2698 | 2020-05-05
2699 | 2020-05-06
2700 | 2020-05-07
2701 | 2020-05-08
2702 | 2020-05-11
2703 | 2020-05-12
2704 | 2020-05-13
2705 | 2020-05-14
2706 | 2020-05-15
2707 | 2020-05-18
2708 | 2020-05-19
2709 | 2020-05-20
2710 | 2020-05-21
2711 | 2020-05-22
2712 | 2020-05-25
2713 | 2020-05-26
2714 | 2020-05-27
2715 | 2020-05-28
2716 | 2020-05-29
2717 | 2020-06-01
2718 | 2020-06-02
2719 | 2020-06-03
2720 | 2020-06-04
2721 | 2020-06-05
2722 | 2020-06-08
2723 | 2020-06-09
2724 | 2020-06-10
2725 | 2020-06-11
2726 | 2020-06-12
2727 | 2020-06-15
2728 | 2020-06-16
2729 | 2020-06-17
2730 | 2020-06-18
2731 | 2020-06-19
2732 | 2020-06-22
2733 | 2020-06-23
2734 | 2020-06-24
2735 | 2020-06-25
2736 | 2020-06-26
2737 | 2020-06-29
2738 | 2020-06-30
2739 | 2020-07-01
2740 | 2020-07-02
2741 | 2020-07-03
2742 | 2020-07-06
2743 | 2020-07-07
2744 | 2020-07-08
2745 | 2020-07-09
2746 | 2020-07-10
2747 | 2020-07-13
2748 | 2020-07-14
2749 | 2020-07-15
2750 | 2020-07-16
2751 | 2020-07-17
2752 | 2020-07-20
2753 | 2020-07-21
2754 | 2020-07-22
2755 | 2020-07-23
2756 | 2020-07-24
2757 | 2020-07-27
2758 | 2020-07-28
2759 | 2020-07-29
2760 | 2020-07-30
2761 | 2020-07-31
2762 | 2020-08-03
2763 | 2020-08-04
2764 | 2020-08-05
2765 | 2020-08-06
2766 | 2020-08-07
2767 | 2020-08-10
2768 | 2020-08-11
2769 | 2020-08-12
2770 | 2020-08-13
2771 | 2020-08-14
2772 | 2020-08-17
2773 | 2020-08-18
2774 | 2020-08-19
2775 | 2020-08-20
2776 | 2020-08-21
2777 | 2020-08-24
2778 | 2020-08-25
2779 | 2020-08-26
2780 | 2020-08-27
2781 | 2020-08-28
2782 | 2020-08-31
2783 | 2020-09-01
2784 | 2020-09-02
2785 | 2020-09-03
2786 | 2020-09-04
2787 | 2020-09-07
2788 | 2020-09-08
2789 | 2020-09-09
2790 | 2020-09-10
2791 | 2020-09-11
2792 | 2020-09-14
2793 | 2020-09-15
2794 | 2020-09-16
2795 | 2020-09-17
2796 | 2020-09-18
2797 | 2020-09-21
2798 | 2020-09-22
2799 | 2020-09-23
2800 | 2020-09-24
2801 | 2020-09-25
2802 | 2020-09-28
2803 | 2020-09-29
2804 | 2020-09-30
2805 | 2020-10-01
2806 | 2020-10-02
2807 | 2020-10-05
2808 | 2020-10-06
2809 | 2020-10-07
2810 | 2020-10-08
2811 | 2020-10-09
2812 | 2020-10-12
2813 | 2020-10-13
2814 | 2020-10-14
2815 | 2020-10-15
2816 | 2020-10-16
2817 | 2020-10-19
2818 | 2020-10-20
2819 | 2020-10-21
2820 | 2020-10-22
2821 | 2020-10-23
2822 | 2020-10-26
2823 | 2020-10-27
2824 | 2020-10-28
2825 | 2020-10-29
2826 | 2020-10-30
2827 | 2020-11-02
2828 | 2020-11-03
2829 | 2020-11-04
2830 | 2020-11-05
2831 | 2020-11-06
2832 | 2020-11-09
2833 | 2020-11-10
2834 | 2020-11-11
2835 | 2020-11-12
2836 | 2020-11-13
2837 | 2020-11-16
2838 | 2020-11-17
2839 | 2020-11-18
2840 | 2020-11-19
2841 | 2020-11-20
2842 | 2020-11-23
2843 | 2020-11-24
2844 | 2020-11-25
2845 | 2020-11-26
2846 | 2020-11-27
2847 | 2020-11-30
2848 | 2020-12-01
2849 | 2020-12-02
2850 | 2020-12-03
2851 | 2020-12-04
2852 | 2020-12-07
2853 | 2020-12-08
2854 | 2020-12-09
2855 | 2020-12-10
2856 | 2020-12-11
2857 | 2020-12-14
2858 | 2020-12-15
2859 | 2020-12-16
2860 | 2020-12-17
2861 | 2020-12-18
2862 | 2020-12-21
2863 | 2020-12-22
2864 | 2020-12-23
2865 | 2020-12-24
2866 | 2020-12-25
2867 | 2020-12-28
2868 | 2020-12-29
2869 | 2020-12-30
2870 | 2020-12-31
2871 | 2021-01-01
2872 | 2021-01-04
2873 | 2021-01-05
2874 | 2021-01-06
2875 | 2021-01-07
2876 | 2021-01-08
2877 | 2021-01-11
2878 | 2021-01-12
2879 | 2021-01-13
2880 | 2021-01-14
2881 | 2021-01-15
2882 | 2021-01-18
2883 | 2021-01-19
2884 | 2021-01-20
2885 | 2021-01-21
2886 | 2021-01-22
2887 | 2021-01-25
2888 | 2021-01-26
2889 | 2021-01-27
2890 | 2021-01-28
2891 | 2021-01-29
2892 | 2021-02-01
2893 | 2021-02-02
2894 | 2021-02-03
2895 | 2021-02-04
2896 | 2021-02-05
2897 | 2021-02-08
2898 | 2021-02-09
2899 | 2021-02-10
2900 | 2021-02-11
2901 | 2021-02-12
2902 | 2021-02-15
2903 | 2021-02-16
2904 | 2021-02-17
2905 | 2021-02-18
2906 | 2021-02-19
2907 | 2021-02-22
2908 | 2021-02-23
2909 | 2021-02-24
2910 | 2021-02-25
2911 | 2021-02-26
2912 | 2021-03-01
2913 | 2021-03-02
2914 | 2021-03-03
2915 | 2021-03-04
2916 | 2021-03-05
2917 | 2021-03-08
2918 | 2021-03-09
2919 | 2021-03-10
2920 | 2021-03-11
2921 | 2021-03-12
2922 | 2021-03-15
2923 | 2021-03-16
2924 | 2021-03-17
2925 | 2021-03-18
2926 | 2021-03-19
2927 | 2021-03-22
2928 | 2021-03-23
2929 | 2021-03-24
2930 | 2021-03-25
2931 | 2021-03-26
2932 | 2021-03-29
2933 | 2021-03-30
2934 | 2021-03-31
2935 | 2021-04-01
2936 | 2021-04-02
2937 | 2021-04-05
2938 | 2021-04-06
2939 | 2021-04-07
2940 | 2021-04-08
2941 | 2021-04-09
2942 | 2021-04-12
2943 | 2021-04-13
2944 | 2021-04-14
2945 | 2021-04-15
2946 | 2021-04-16
2947 | 2021-04-19
2948 | 2021-04-20
2949 | 2021-04-21
2950 | 2021-04-22
2951 | 2021-04-23
2952 | 2021-04-26
2953 | 2021-04-27
2954 | 2021-04-28
2955 | 2021-04-29
2956 | 2021-04-30
2957 | 2021-05-03
2958 | 2021-05-04
2959 | 2021-05-05
2960 | 2021-05-06
2961 | 2021-05-07
2962 | 2021-05-10
2963 | 2021-05-11
2964 | 2021-05-12
2965 | 2021-05-13
2966 | 2021-05-14
2967 | 2021-05-17
2968 | 2021-05-18
2969 | 2021-05-19
2970 | 2021-05-20
2971 | 2021-05-21
2972 | 2021-05-24
2973 | 2021-05-25
2974 | 2021-05-26
2975 | 2021-05-27
2976 | 2021-05-28
2977 | 2021-05-31
2978 | 2021-06-01
2979 | 2021-06-02
2980 | 2021-06-03
2981 | 2021-06-04
2982 | 2021-06-07
2983 | 2021-06-08
2984 | 2021-06-09
2985 | 2021-06-10
2986 | 2021-06-11
2987 | 2021-06-14
2988 | 2021-06-15
2989 | 2021-06-16
2990 | 2021-06-17
2991 | 2021-06-18
2992 | 2021-06-21
2993 | 2021-06-22
2994 | 2021-06-23
2995 | 2021-06-24
2996 | 2021-06-25
2997 | 2021-06-28
2998 | 2021-06-29
2999 | 2021-06-30
3000 | 2021-07-01
3001 | 2021-07-02
3002 | 2021-07-05
3003 | 2021-07-06
3004 | 2021-07-07
3005 | 2021-07-08
3006 | 2021-07-09
3007 | 2021-07-12
3008 | 2021-07-13
3009 | 2021-07-14
3010 | 2021-07-15
3011 | 2021-07-16
3012 | 2021-07-19
3013 | 2021-07-20
3014 | 2021-07-21
3015 | 2021-07-22
3016 | 2021-07-23
3017 | 2021-07-26
3018 | 2021-07-27
3019 | 2021-07-28
3020 | 2021-07-29
3021 | 2021-07-30
3022 | 2021-08-02
3023 | 2021-08-03
3024 | 2021-08-04
3025 | 2021-08-05
3026 | 2021-08-06
3027 | 2021-08-09
3028 | 2021-08-10
3029 | 2021-08-11
3030 | 2021-08-12
3031 | 2021-08-13
3032 | 2021-08-16
3033 | 2021-08-17
3034 | 2021-08-18
3035 | 2021-08-19
3036 | 2021-08-20
3037 | 2021-08-23
3038 | 2021-08-24
3039 | 2021-08-25
3040 | 2021-08-26
3041 | 2021-08-27
3042 | 2021-08-30
3043 | 2021-08-31
3044 | 2021-09-01
3045 | 2021-09-02
3046 | 2021-09-03
3047 | 2021-09-06
3048 | 2021-09-07
3049 | 2021-09-08
3050 | 2021-09-09
3051 | 2021-09-10
3052 | 2021-09-13
3053 | 2021-09-14
3054 | 2021-09-15
3055 | 2021-09-16
3056 | 2021-09-17
3057 | 2021-09-20
3058 | 2021-09-21
3059 | 2021-09-22
3060 | 2021-09-23
3061 | 2021-09-24
3062 | 2021-09-27
3063 | 2021-09-28
3064 | 2021-09-29
3065 | 2021-09-30
3066 | 2021-10-01
3067 | 2021-10-04
3068 | 2021-10-05
3069 | 2021-10-06
3070 | 2021-10-07
3071 | 2021-10-08
3072 | 2021-10-11
3073 | 2021-10-12
3074 | 2021-10-13
3075 | 2021-10-14
3076 | 2021-10-15
3077 | 2021-10-18
3078 | 2021-10-19
3079 | 2021-10-20
3080 | 2021-10-21
3081 | 2021-10-22
3082 | 2021-10-25
3083 | 2021-10-26
3084 | 2021-10-27
3085 | 2021-10-28
3086 | 2021-10-29
3087 | 2021-11-01
3088 | 2021-11-02
3089 | 2021-11-03
3090 | 2021-11-04
3091 | 2021-11-05
3092 | 2021-11-08
3093 | 2021-11-09
3094 | 2021-11-10
3095 | 2021-11-11
3096 | 2021-11-12
3097 | 2021-11-15
3098 | 2021-11-16
3099 | 2021-11-17
3100 | 2021-11-18
3101 | 2021-11-19
3102 | 2021-11-22
3103 | 2021-11-23
3104 | 2021-11-24
3105 | 2021-11-25
3106 | 2021-11-26
3107 | 2021-11-29
3108 | 2021-11-30
3109 | 2021-12-01
3110 | 2021-12-02
3111 | 2021-12-03
3112 | 2021-12-06
3113 | 2021-12-07
3114 | 2021-12-08
3115 | 2021-12-09
3116 | 2021-12-10
3117 | 2021-12-13
3118 | 2021-12-14
3119 | 2021-12-15
3120 | 2021-12-16
3121 | 2021-12-17
3122 | 2021-12-20
3123 | 2021-12-21
3124 | 2021-12-22
3125 | 2021-12-23
3126 | 2021-12-24
3127 | 2021-12-27
3128 | 2021-12-28
3129 | 2021-12-29
3130 | 2021-12-30
3131 | 2021-12-31
3132 | 2022-01-03
3133 | 2022-01-04
3134 | 2022-01-05
3135 | 2022-01-06
3136 | 2022-01-07
3137 | 2022-01-10
3138 | 2022-01-11
3139 | 2022-01-12
3140 | 2022-01-13
3141 | 2022-01-14
3142 | 2022-01-17
3143 | 2022-01-18
3144 | 2022-01-19
3145 | 2022-01-20
3146 | 2022-01-21
3147 | 2022-01-24
3148 | 2022-01-25
3149 | 2022-01-26
3150 | 2022-01-27
3151 | 2022-01-28
3152 | 2022-01-31
3153 | 2022-02-01
3154 | 2022-02-02
3155 | 2022-02-03
3156 | 2022-02-04
3157 | 2022-02-07
3158 | 2022-02-08
3159 | 2022-02-09
3160 | 2022-02-10
3161 | 2022-02-11
3162 | 2022-02-14
3163 | 2022-02-15
3164 | 2022-02-16
3165 | 2022-02-17
3166 | 2022-02-18
3167 | 2022-02-21
3168 | 2022-02-22
3169 | 2022-02-23
3170 | 2022-02-24
3171 | 2022-02-25
3172 | 2022-02-28
3173 | 2022-03-01
3174 | 2022-03-02
3175 | 2022-03-03
3176 | 2022-03-04
3177 | 2022-03-07
3178 | 2022-03-08
3179 | 2022-03-09
3180 | 2022-03-10
3181 | 2022-03-11
3182 | 2022-03-14
3183 | 2022-03-15
3184 | 2022-03-16
3185 | 2022-03-17
3186 | 2022-03-18
3187 | 2022-03-21
3188 | 2022-03-22
3189 | 2022-03-23
3190 | 2022-03-24
3191 | 2022-03-25
3192 | 2022-03-28
3193 | 2022-03-29
3194 | 2022-03-30
3195 | 2022-03-31
3196 | 2022-04-01
3197 | 2022-04-04
3198 | 2022-04-05
3199 | 2022-04-06
3200 | 2022-04-07
3201 | 2022-04-08
3202 | 2022-04-11
3203 | 2022-04-12
3204 | 2022-04-13
3205 | 2022-04-14
3206 | 2022-04-15
3207 | 2022-04-18
3208 | 2022-04-19
3209 | 2022-04-20
3210 | 2022-04-21
3211 | 2022-04-22
3212 | 2022-04-25
3213 | 2022-04-26
3214 | 2022-04-27
3215 | 2022-04-28
3216 | 2022-04-29
3217 | 2022-05-02
3218 | 2022-05-03
3219 | 2022-05-04
3220 | 2022-05-05
3221 | 2022-05-06
3222 | 2022-05-09
3223 | 2022-05-10
3224 | 2022-05-11
3225 | 2022-05-12
3226 | 2022-05-13
3227 | 2022-05-16
3228 | 2022-05-17
3229 | 2022-05-18
3230 | 2022-05-19
3231 | 2022-05-20
3232 | 2022-05-23
3233 | 2022-05-24
3234 | 2022-05-25
3235 | 2022-05-26
3236 | 2022-05-27
3237 | 2022-05-30
3238 | 2022-05-31
3239 | 2022-06-01
3240 | 2022-06-02
3241 | 2022-06-03
3242 | 2022-06-06
3243 | 2022-06-07
3244 | 2022-06-08
3245 | 2022-06-09
3246 | 2022-06-10
3247 | 2022-06-13
3248 | 2022-06-14
3249 | 2022-06-15
3250 | 2022-06-16
3251 | 2022-06-17
3252 | 2022-06-20
3253 | 2022-06-21
3254 | 2022-06-22
3255 | 2022-06-23
3256 | 2022-06-24
3257 | 2022-06-27
3258 | 2022-06-28
3259 | 2022-06-29
3260 | 2022-06-30
3261 | 2022-07-01
3262 | 2022-07-04
3263 | 2022-07-05
3264 | 2022-07-06
3265 | 2022-07-07
3266 | 2022-07-08
3267 | 2022-07-11
3268 | 2022-07-12
3269 | 2022-07-13
3270 | 2022-07-14
3271 | 2022-07-15
3272 | 2022-07-18
3273 | 2022-07-19
3274 | 2022-07-20
3275 | 2022-07-21
3276 | 2022-07-22
3277 | 2022-07-25
3278 | 2022-07-26
3279 | 2022-07-27
3280 | 2022-07-28
3281 | 2022-07-29
3282 | 2022-08-01
3283 | 2022-08-02
3284 | 2022-08-03
3285 | 2022-08-04
3286 | 2022-08-05
3287 | 2022-08-08
3288 | 2022-08-09
3289 | 2022-08-10
3290 | 2022-08-11
3291 | 2022-08-12
3292 | 2022-08-15
3293 | 2022-08-16
3294 | 2022-08-17
3295 | 2022-08-18
3296 | 2022-08-19
3297 | 2022-08-22
3298 | 2022-08-23
3299 | 2022-08-24
3300 | 2022-08-25
3301 | 2022-08-26
3302 | 2022-08-29
3303 | 2022-08-30
3304 | 2022-08-31
3305 | 2022-09-01
3306 | 2022-09-02
3307 | 2022-09-05
3308 | 2022-09-06
3309 | 2022-09-07
3310 | 2022-09-08
3311 | 2022-09-09
3312 | 2022-09-12
3313 | 2022-09-13
3314 | 2022-09-14
3315 | 2022-09-15
3316 | 2022-09-16
3317 | 2022-09-19
3318 | 2022-09-20
3319 | 2022-09-21
3320 | 2022-09-22
3321 | 2022-09-23
3322 | 2022-09-26
3323 | 2022-09-27
3324 | 2022-09-28
3325 | 2022-09-29
3326 | 2022-09-30
3327 | 2022-10-03
3328 | 2022-10-04
3329 | 2022-10-05
3330 | 2022-10-06
3331 | 2022-10-07
3332 | 2022-10-10
3333 | 2022-10-11
3334 | 2022-10-12
3335 | 2022-10-13
3336 | 2022-10-14
3337 | 2022-10-17
3338 | 2022-10-18
3339 | 2022-10-19
3340 | 2022-10-20
3341 | 2022-10-21
3342 | 2022-10-24
3343 | 2022-10-25
3344 | 2022-10-26
3345 | 2022-10-27
3346 | 2022-10-28
3347 | 2022-10-31
3348 | 2022-11-01
3349 | 2022-11-02
3350 | 2022-11-03
3351 | 2022-11-04
3352 | 2022-11-07
3353 | 2022-11-08
3354 | 2022-11-09
3355 | 2022-11-10
3356 | 2022-11-11
3357 | 2022-11-14
3358 | 2022-11-15
3359 | 2022-11-16
3360 | 2022-11-17
3361 | 2022-11-18
3362 | 2022-11-21
3363 | 2022-11-22
3364 | 2022-11-23
3365 | 2022-11-24
3366 | 2022-11-25
3367 | 2022-11-28
3368 | 2022-11-29
3369 | 2022-11-30
3370 | 2022-12-01
3371 | 2022-12-02
3372 | 2022-12-05
3373 | 2022-12-06
3374 | 2022-12-07
3375 | 2022-12-08
3376 | 2022-12-09
3377 | 2022-12-12
3378 | 2022-12-13
3379 | 2022-12-14
3380 | 2022-12-15
3381 | 2022-12-16
3382 | 2022-12-19
3383 | 2022-12-20
3384 | 2022-12-21
3385 | 2022-12-22
3386 | 2022-12-23
3387 | 2022-12-26
3388 | 2022-12-27
3389 | 2022-12-28
3390 | 2022-12-29
3391 | 2022-12-30
3392 | 2023-01-02
3393 | 2023-01-03
3394 | 2023-01-04
3395 | 2023-01-05
3396 | 2023-01-06
3397 | 2023-01-09
3398 | 2023-01-10
3399 | 2023-01-11
3400 | 2023-01-12
3401 | 2023-01-13
3402 | 2023-01-16
3403 | 2023-01-17
3404 | 2023-01-18
3405 | 2023-01-19
3406 | 2023-01-20
3407 | 2023-01-23
3408 | 2023-01-24
3409 | 2023-01-25
3410 | 2023-01-26
3411 | 2023-01-27
3412 | 2023-01-30
3413 | 2023-01-31
3414 | 2023-02-01
3415 | 2023-02-02
3416 | 2023-02-03
3417 | 2023-02-06
3418 | 2023-02-07
3419 | 2023-02-08
3420 | 2023-02-09
3421 | 2023-02-10
3422 | 2023-02-13
3423 | 2023-02-14
3424 | 2023-02-15
3425 | 2023-02-16
3426 | 2023-02-17
3427 | 2023-02-20
3428 | 2023-02-21
3429 | 2023-02-22
3430 | 2023-02-23
3431 | 2023-02-24
3432 | 2023-02-27
3433 | 2023-02-28
3434 | 2023-03-01
3435 | 2023-03-02
3436 | 2023-03-03
3437 | 2023-03-06
3438 | 2023-03-07
3439 | 2023-03-08
3440 | 2023-03-09
3441 | 2023-03-10
3442 | 2023-03-13
3443 | 2023-03-14
3444 | 2023-03-15
3445 | 2023-03-16
3446 | 2023-03-17
3447 | 2023-03-20
3448 | 2023-03-21
3449 | 2023-03-22
3450 | 2023-03-23
3451 | 2023-03-24
3452 | 2023-03-27
3453 | 2023-03-28
3454 | 2023-03-29
3455 | 2023-03-30
3456 | 2023-03-31
3457 | 2023-04-03
3458 | 2023-04-04
3459 | 2023-04-05
3460 | 2023-04-06
3461 | 2023-04-07
3462 | 2023-04-10
3463 | 2023-04-11
3464 | 2023-04-12
3465 | 2023-04-13
3466 | 2023-04-14
3467 | 2023-04-17
3468 | 2023-04-18
3469 | 2023-04-19
3470 | 2023-04-20
3471 | 2023-04-21
3472 | 2023-04-24
3473 | 2023-04-25
3474 | 2023-04-26
3475 | 2023-04-27
3476 | 2023-04-28
3477 | 2023-05-01
3478 | 2023-05-02
3479 | 2023-05-03
3480 | 2023-05-04
3481 | 2023-05-05
3482 | 2023-05-08
3483 | 2023-05-09
3484 | 2023-05-10
3485 | 2023-05-11
3486 | 2023-05-12
3487 | 2023-05-15
3488 | 2023-05-16
3489 | 2023-05-17
3490 | 2023-05-18
3491 | 2023-05-19
3492 | 2023-05-22
3493 | 2023-05-23
3494 | 2023-05-24
3495 | 2023-05-25
3496 | 2023-05-26
3497 | 2023-05-29
3498 | 2023-05-30
3499 | 2023-05-31
3500 | 2023-06-01
3501 | 2023-06-02
3502 | 2023-06-05
3503 | 2023-06-06
3504 | 2023-06-07
3505 | 2023-06-08
3506 | 2023-06-09
3507 | 2023-06-12
3508 | 2023-06-13
3509 | 2023-06-14
3510 | 2023-06-15
3511 | 2023-06-16
3512 | 2023-06-19
3513 | 2023-06-20
3514 | 2023-06-21
3515 | 2023-06-22
3516 | 2023-06-23
3517 | 2023-06-26
3518 | 2023-06-27
3519 | 2023-06-28
3520 | 2023-06-29
3521 | 2023-06-30
3522 | 2023-07-03
3523 | 2023-07-04
3524 | 2023-07-05
3525 | 2023-07-06
3526 | 2023-07-07
3527 | 2023-07-10
3528 | 2023-07-11
3529 | 2023-07-12
3530 | 2023-07-13
3531 | 2023-07-14
3532 | 2023-07-17
3533 | 2023-07-18
3534 | 2023-07-19
3535 | 2023-07-20
3536 | 2023-07-21
3537 | 2023-07-24
3538 | 2023-07-25
3539 | 2023-07-26
3540 | 2023-07-27
3541 | 2023-07-28
3542 | 2023-07-31
3543 | 2023-08-01
3544 | 2023-08-02
3545 | 2023-08-03
3546 | 2023-08-04
3547 | 2023-08-07
3548 | 2023-08-08
3549 | 2023-08-09
3550 | 2023-08-10
3551 | 2023-08-11
3552 | 2023-08-14
3553 | 2023-08-15
3554 | 2023-08-16
3555 | 2023-08-17
3556 | 2023-08-18
3557 | 2023-08-21
3558 | 2023-08-22
3559 | 2023-08-23
3560 | 2023-08-24
3561 | 2023-08-25
3562 | 2023-08-28
3563 | 2023-08-29
3564 | 2023-08-30
3565 | 2023-08-31
3566 | 2023-09-01
3567 | 2023-09-04
3568 | 2023-09-05
3569 | 2023-09-06
3570 | 2023-09-07
3571 | 2023-09-08
3572 | 2023-09-11
3573 | 2023-09-12
3574 | 2023-09-13
3575 | 2023-09-14
3576 | 2023-09-15
3577 | 2023-09-18
3578 | 2023-09-19
3579 | 2023-09-20
3580 | 2023-09-21
3581 | 2023-09-22
3582 | 2023-09-25
3583 | 2023-09-26
3584 | 2023-09-27
3585 | 2023-09-28
3586 | 2023-09-29
3587 | 2023-10-02
3588 | 2023-10-03
3589 | 2023-10-04
3590 | 2023-10-05
3591 | 2023-10-06
3592 | 2023-10-09
3593 | 2023-10-10
3594 | 2023-10-11
3595 | 2023-10-12
3596 | 2023-10-13
3597 | 2023-10-16
3598 | 2023-10-17
3599 | 2023-10-18
3600 | 2023-10-19
3601 | 2023-10-20
3602 | 2023-10-23
3603 | 2023-10-24
3604 | 2023-10-25
3605 | 2023-10-26
3606 | 2023-10-27
3607 | 2023-10-30
3608 | 2023-10-31
3609 | 2023-11-01
3610 | 2023-11-02
3611 | 2023-11-03
3612 | 2023-11-06
3613 | 2023-11-07
3614 | 2023-11-08
3615 | 2023-11-09
3616 | 2023-11-10
3617 | 2023-11-13
3618 | 2023-11-14
3619 | 2023-11-15
3620 | 2023-11-16
3621 | 2023-11-17
3622 | 2023-11-20
3623 | 2023-11-21
3624 | 2023-11-22
3625 | 2023-11-23
3626 | 2023-11-24
3627 | 2023-11-27
3628 | 2023-11-28
3629 | 2023-11-29
3630 | 2023-11-30
3631 | 2023-12-01
3632 | 2023-12-04
3633 | 2023-12-05
3634 | 2023-12-06
3635 | 2023-12-07
3636 | 2023-12-08
3637 | 2023-12-11
3638 | 2023-12-12
3639 | 2023-12-13
3640 | 2023-12-14
3641 | 2023-12-15
3642 | 2023-12-18
3643 | 2023-12-19
3644 | 2023-12-20
3645 | 2023-12-21
3646 | 2023-12-22
3647 | 2023-12-25
3648 | 2023-12-26
3649 | 2023-12-27
3650 | 2023-12-28
3651 | 2023-12-29
3652 | 2024-01-01
3653 | 2024-01-02
3654 | 2024-01-03
3655 | 2024-01-04
3656 | 2024-01-05
3657 | 2024-01-08
3658 | 2024-01-09
3659 | 2024-01-10
3660 | 2024-01-11
3661 | 2024-01-12
3662 | 2024-01-15
3663 | 2024-01-16
3664 | 2024-01-17
3665 | 2024-01-18
3666 | 2024-01-19
3667 | 2024-01-22
3668 | 2024-01-23
3669 | 2024-01-24
3670 | 2024-01-25
3671 | 2024-01-26
3672 | 2024-01-29
3673 | 2024-01-30
3674 | 2024-01-31
3675 | 2024-02-01
3676 | 2024-02-02
3677 | 2024-02-05
3678 | 2024-02-06
3679 | 2024-02-07
3680 | 2024-02-08
3681 | 2024-02-09
3682 | 2024-02-12
3683 | 2024-02-13
3684 | 2024-02-14
3685 | 2024-02-15
3686 | 2024-02-16
3687 | 2024-02-19
3688 | 2024-02-20
3689 | 2024-02-21
3690 | 2024-02-22
3691 | 2024-02-23
3692 | 2024-02-26
3693 | 2024-02-27
3694 | 2024-02-28
3695 | 2024-02-29
3696 | 2024-03-01
3697 | 2024-03-04
3698 | 2024-03-05
3699 | 2024-03-06
3700 | 2024-03-07
3701 | 2024-03-08
3702 | 2024-03-11
3703 | 2024-03-12
3704 | 2024-03-13
3705 | 2024-03-14
3706 | 2024-03-15
3707 | 2024-03-18
3708 | 2024-03-19
3709 | 2024-03-20
3710 | 2024-03-21
3711 | 2024-03-22
3712 | 2024-03-25
3713 | 2024-03-26
3714 | 2024-03-27
3715 | 2024-03-28
3716 | 2024-03-29
3717 | 2024-04-01
3718 | 2024-04-02
3719 | 2024-04-03
3720 | 2024-04-04
3721 | 2024-04-05
3722 | 2024-04-08
3723 | 2024-04-09
3724 | 2024-04-10
3725 | 2024-04-11
3726 | 2024-04-12
3727 | 2024-04-15
3728 | 2024-04-16
3729 | 2024-04-17
3730 | 2024-04-18
3731 | 2024-04-19
3732 | 2024-04-22
3733 | 2024-04-23
3734 | 2024-04-24
3735 | 2024-04-25
3736 | 2024-04-26
3737 | 2024-04-29
3738 | 2024-04-30
3739 | 2024-05-01
3740 | 2024-05-02
3741 | 2024-05-03
3742 | 2024-05-06
3743 | 2024-05-07
3744 | 2024-05-08
3745 | 2024-05-09
3746 | 2024-05-10
3747 | 2024-05-13
3748 | 2024-05-14
3749 | 2024-05-15
3750 | 2024-05-16
3751 | 2024-05-17
3752 | 2024-05-20
3753 | 2024-05-21
3754 | 2024-05-22
3755 | 2024-05-23
3756 | 2024-05-24
3757 | 2024-05-27
3758 | 2024-05-28
3759 | 2024-05-29
3760 | 2024-05-30
3761 | 2024-05-31
3762 | 2024-06-03
3763 | 2024-06-04
3764 | 2024-06-05
3765 | 2024-06-06
3766 | 2024-06-07
3767 | 2024-06-10
3768 | 2024-06-11
3769 | 2024-06-12
3770 | 2024-06-13
3771 | 2024-06-14
3772 | 2024-06-17
3773 | 2024-06-18
3774 | 2024-06-19
3775 | 2024-06-20
3776 | 2024-06-21
3777 | 2024-06-24
3778 | 2024-06-25
3779 | 2024-06-26
3780 | 2024-06-27
3781 | 2024-06-28
3782 | 2024-07-01
3783 | 2024-07-02
3784 | 2024-07-03
3785 | 2024-07-04
3786 | 2024-07-05
3787 | 2024-07-08
3788 | 2024-07-09
3789 | 2024-07-10
3790 | 2024-07-11
3791 | 2024-07-12
3792 | 2024-07-15
3793 | 2024-07-16
3794 | 2024-07-17
3795 | 2024-07-18
3796 | 2024-07-19
3797 | 2024-07-22
3798 | 2024-07-23
3799 | 2024-07-24
3800 | 2024-07-25
3801 | 2024-07-26
3802 | 2024-07-29
3803 | 2024-07-30
3804 | 2024-07-31
3805 | 2024-08-01
3806 | 2024-08-02
3807 | 2024-08-05
3808 | 2024-08-06
3809 | 2024-08-07
3810 | 2024-08-08
3811 | 2024-08-09
3812 | 2024-08-12
3813 | 2024-08-13
3814 | 2024-08-14
3815 | 2024-08-15
3816 | 2024-08-16
3817 | 2024-08-19
3818 | 2024-08-20
3819 | 2024-08-21
3820 | 2024-08-22
3821 | 2024-08-23
3822 | 2024-08-26
3823 | 2024-08-27
3824 | 2024-08-28
3825 | 2024-08-29
3826 | 2024-08-30
3827 | 2024-09-02
3828 | 2024-09-03
3829 | 2024-09-04
3830 | 2024-09-05
3831 | 2024-09-06
3832 | 2024-09-09
3833 | 2024-09-10
3834 | 2024-09-11
3835 | 2024-09-12
3836 | 2024-09-13
3837 | 2024-09-16
3838 | 2024-09-17
3839 | 2024-09-18
3840 | 2024-09-19
3841 | 2024-09-20
3842 | 2024-09-23
3843 | 2024-09-24
3844 | 2024-09-25
3845 | 2024-09-26
3846 | 2024-09-27
3847 | 2024-09-30
3848 | 2024-10-01
3849 | 2024-10-02
3850 | 2024-10-03
3851 | 2024-10-04
3852 | 2024-10-07
3853 | 2024-10-08
3854 | 2024-10-09
3855 | 2024-10-10
3856 | 2024-10-11
3857 | 2024-10-14
3858 | 2024-10-15
3859 | 2024-10-16
3860 | 2024-10-17
3861 | 2024-10-18
3862 | 2024-10-21
3863 | 2024-10-22
3864 | 2024-10-23
3865 | 2024-10-24
3866 | 2024-10-25
3867 | 2024-10-28
3868 | 2024-10-29
3869 | 2024-10-30
3870 | 2024-10-31
3871 | 2024-11-01
3872 | 2024-11-04
3873 | 2024-11-05
3874 | 2024-11-06
3875 | 2024-11-07
3876 | 2024-11-08
3877 | 2024-11-11
3878 | 2024-11-12
3879 | 2024-11-13
3880 | 2024-11-14
3881 | 2024-11-15
3882 | 2024-11-18
3883 | 2024-11-19
3884 | 2024-11-20
3885 | 2024-11-21
3886 | 2024-11-22
3887 | 2024-11-25
3888 | 2024-11-26
3889 | 2024-11-27
3890 | 2024-11-28
3891 | 2024-11-29
3892 | 2024-12-02
3893 | 2024-12-03
3894 | 2024-12-04
3895 | 2024-12-05
3896 | 2024-12-06
3897 | 2024-12-09
3898 | 2024-12-10
3899 | 2024-12-11
3900 | 2024-12-12
3901 | 2024-12-13
3902 | 2024-12-16
3903 | 2024-12-17
3904 | 2024-12-18
3905 | 2024-12-19
3906 | 2024-12-20
3907 | 2024-12-23
3908 | 2024-12-24
3909 | 2024-12-25
3910 | 2024-12-26
3911 | 2024-12-27
3912 | 2024-12-30
3913 | 2024-12-31
3914 | 2025-01-01