## resources
staff | capacity | team | contract
andrea | 40 | research | fte
delanie | 100 | research | intern
harrison | 100 | research | fte
hunter | 100 | research | intern
isabella | 100 | research | intern
mohib | 100 | research | fte
murray | 100 | research | fte
nick | 100 | research | intern
paulo | 100 | research | fte
steve | 100 | leadership | fte
talia | 100 | research | fte
thom | 100 | research | fte
unassigned | 100 | research | fte
wallace | 100 | comms | fte
zak | 100 | research | fte

## projects
project | probability.of.occuring | kickoff | launch
SDG16 | 1 | 2019-01-18 | 2019-03-18
DFAT | 1 | 2019-01-18 | 2019-02-18
MPI | 1 | 2019-01-18 | 2019-04-09
CEF | 1 | 2019-01-25 | 2019-05-01
Risk Paper | 1 | 2019-05-30 | 2019-07-31
GPI | 1 | 2019-02-20 | 2019-05-30
Normandy Peace Index | 0.5 | 2019-03-01 | 2019-06-06
WISPI Update | 0.5 | 2019-04-01 | 2019-06-06
UNDP Addis | 1 | 2019-01-21 | 2019-02-27
Finance and Peace | 1 | 2019-01-18 | 2019-03-21
PPI | 1 | 2019-08-01 | 2019-10-30
GTI | 1 | 2019-08-01 | 2019-11-25
SESHAT | 1 | 2019-06-01 | 2019-09-30
KAS | 0.5 | 2019-02-18 | 2019-03-28
maintenance | 1 | 2019-02-01 | 2019-06-30

## phases
id | phases | dependencies
1 | research | 0
2 | drafting | 1
3 | editing | 2
4 | design | 3
5 | print | 4
6 | events | 5

## roles
roles
lead
researcher
editor
design

## leave
staff | start | end | description
thom | 2019-02-11 | 2019-02-22 | leave
steve | 2019-03-03 | 2019-03-08 | Melbourne
steve | 2019-03-25 | 2019-04-15 | Oslo
steve | 2019-05-13 | 2019-07-01 | GPI
Formulas:
end = [start]+7*7

## public holidays
holiday | holiday.dates
New Year's Day | 1 January 2019
2Australia Day | 28 January 2019
Good Friday | 19 April 2019
Easter Saturday | 20 April 2019
Easter Sunday | 21 April 2019
Easter Monday | 22 April 2019
Anzac Day | 25 April 2019
Queen's Birthday | 10 June 2019
1Bank Holiday | 5 August 2019
Labour Day | 7 October 2019
Christmas Day | 25 December 2019
Boxing Day | 26 December 2019

## teams
project | staff | role | workshare
DFAT | andrea
UNDP Addis | andrea
SDG16 | andrea
Finance and Peace | andrea
KAS | andrea
MPI | andrea
CEF | andrea
GPI | andrea
Normandy Peace Index | andrea
WISPI Update | andrea
maintenance | andrea
Risk Paper | andrea
SESHAT | andrea
PPI | andrea
GTI | andrea
DFAT | delanie
UNDP Addis | delanie
SDG16 | delanie
Finance and Peace | delanie
KAS | delanie
MPI | delanie
CEF | delanie
GPI | delanie
Normandy Peace Index | delanie
WISPI Update | delanie
maintenance | delanie
Risk Paper | delanie
SESHAT | delanie
PPI | delanie
GTI | delanie
DFAT | harrison
UNDP Addis | harrison
SDG16 | harrison
Finance and Peace | harrison
KAS | harrison
MPI | harrison
CEF | harrison
GPI | harrison
Normandy Peace Index | harrison
WISPI Update | harrison
maintenance | harrison
Risk Paper | harrison
SESHAT | harrison
PPI | harrison
GTI | harrison
DFAT | hunter
UNDP Addis | hunter
SDG16 | hunter
Finance and Peace | hunter
KAS | hunter
MPI | hunter
CEF | hunter
GPI | hunter
Normandy Peace Index | hunter
WISPI Update | hunter
maintenance | hunter
Risk Paper | hunter
SESHAT | hunter
PPI | hunter
GTI | hunter
DFAT | isabella
UNDP Addis | isabella
SDG16 | isabella
Finance and Peace | isabella
KAS | isabella
MPI | isabella
CEF | isabella
GPI | isabella
Normandy Peace Index | isabella
WISPI Update | isabella
maintenance | isabella
Risk Paper | isabella
SESHAT | isabella
PPI | isabella
GTI | isabella
DFAT | mohib
UNDP Addis | mohib
SDG16 | mohib
Finance and Peace | mohib
KAS | mohib
MPI | mohib
CEF | mohib
GPI | mohib
Normandy Peace Index | mohib
WISPI Update | mohib
maintenance | mohib
Risk Paper | mohib
SESHAT | mohib
PPI | mohib
GTI | mohib
DFAT | murray
UNDP Addis | murray
SDG16 | murray
Finance and Peace | murray
KAS | murray
MPI | murray
CEF | murray
GPI | murray
Normandy Peace Index | murray
WISPI Update | murray
maintenance | murray
Risk Paper | murray
SESHAT | murray
PPI | murray
GTI | murray
DFAT | nick
UNDP Addis | nick
SDG16 | nick
Finance and Peace | nick
KAS | nick
MPI | nick
CEF | nick
GPI | nick
Normandy Peace Index | nick
WISPI Update | nick
maintenance | nick
Risk Paper | nick
SESHAT | nick
PPI | nick
GTI | nick
DFAT | paulo
UNDP Addis | paulo
SDG16 | paulo
Finance and Peace | paulo
KAS | paulo
MPI | paulo
CEF | paulo
GPI | paulo
Normandy Peace Index | paulo
WISPI Update | paulo
maintenance | paulo
Risk Paper | paulo
SESHAT | paulo
PPI | paulo
GTI | paulo
DFAT | steve
UNDP Addis | steve
SDG16 | steve
Finance and Peace | steve
KAS | steve
MPI | steve
CEF | steve
GPI | steve
Normandy Peace Index | steve
WISPI Update | steve
maintenance | steve
Risk Paper | steve
SESHAT | steve
PPI | steve
GTI | steve
DFAT | talia
UNDP Addis | talia
SDG16 | talia
Finance and Peace | talia
KAS | talia
MPI | talia
CEF | talia
GPI | talia
Normandy Peace Index | talia
WISPI Update | talia
maintenance | talia
Risk Paper | talia
SESHAT | talia
PPI | talia
GTI | talia
DFAT | thom
UNDP Addis | thom
SDG16 | thom
Finance and Peace | thom
KAS | thom
MPI | thom
CEF | thom
GPI | thom
Normandy Peace Index | thom
WISPI Update | thom
maintenance | thom
Risk Paper | thom
SESHAT | thom
PPI | thom
GTI | thom
DFAT | unassigned
UNDP Addis | unassigned
SDG16 | unassigned
Finance and Peace | unassigned
KAS | unassigned
MPI | unassigned
CEF | unassigned
GPI | unassigned
Normandy Peace Index | unassigned
WISPI Update | unassigned
maintenance | unassigned
Risk Paper | unassigned
SESHAT | unassigned
PPI | unassigned
GTI | unassigned
DFAT | wallace
UNDP Addis | wallace
SDG16 | wallace
Finance and Peace | wallace
KAS | wallace
MPI | wallace
CEF | wallace
GPI | wallace
Normandy Peace Index | wallace
WISPI Update | wallace
maintenance | wallace
Risk Paper | wallace
SESHAT | wallace
PPI | wallace
GTI | wallace
DFAT | zak
UNDP Addis | zak
SDG16 | zak
Finance and Peace | zak
KAS | zak
MPI | zak
CEF | zak
GPI | zak
Normandy Peace Index | zak
WISPI Update | zak
maintenance | zak
Risk Paper | zak
SESHAT | zak
PPI | zak
GTI | zak