## resources
staff | capacity | team | contract
Cornejo, Cierra | 1 | C | FTE
Jones, Josiah | 1 | A | INTERN
Proano Rodriguez, Leopoldo | 1 | A | FTE
Boon, Kevin | 1 | C | FTE
Compton, Ebony | 1 | C | INTERN
unassigned | 1

## projects
project | probability | launch
O | 1 | 2019-06-03
N | 1 | 2019-07-17
E | 0.5 | 2019-08-10
V | 1 | 2019-08-15
W | 0.5 | 2019-09-14
K | 0.5 | 2019-09-27
T | 1 | 2019-11-15
D | 0.5 | 2019-12-12
Z | 1 | 2019-12-18
A | 0.5 | 2020-01-23

## project.phases
phase | sequencing
research | 1
drafting | 2
editing | 3
design | 4
print | 5
launch-events | 6

## roles
role
lead
researcher
editor
design

## public.holidays
date | holiday.name | information
2019-01-01 | New Year's Day | New Year's Day is the first day of the calendar year and is celebrated each January 1st
2019-01-28 | Australia Day | Always celebrated on 26 January
2019-04-19 | Good Friday | Easter is celebrated with Good Friday and Easter Monday creating a 4 day long weekend.
2019-04-20 | Saturday before Easter Sunday | Easter Saturday is between Good Friday and Easter Sunday in Australia.
2019-04-21 | Easter Sunday | Public Holiday as part of Easter.
2019-04-22 | Easter Monday | Public Holiday as part of Easter.
2019-04-25 | Anzac Day | Celebrated on the 25 April each year.
2019-06-10 | Queen's Birthday | Celebrated on second Monday in June except in Western Australia and Queensland.
2019-08-05 | Bank Holiday | Applies to banks and certain financial institutions, per theÊRetail Trading Act 2008
2019-10-07 | Labour Day | Always on a Monday, creating a long weekend. It celebrates the eight-hour working day, a victory for workers in the mid-late 19th century.
2019-12-25 | Christmas Day | Christmas Day is an annual holiday which celebrates the birth of Jesus Christ over 2000 years ago.
2019-12-26 | Boxing Day | Boxing Day occurs the day after Christmas. Sydney-to-Hobart yacht race and Boxing Day Test Match (Cricket) start on this day.

## leave
leave.id | staff | start | end
1 | Boon, Kevin | 2019-05-31 | 2019-06-14
2 | Boon, Kevin | 2019-05-28 | 2019-06-04
3 | Proano Rodriguez, Leopoldo | 2019-05-08 | 2019-05-29

## responsibilities
role | research | drafting | editing | design | print | launch-events
lead | 1 | 1 | 1 | 1 | 1 | 1
researcher | 1 | 1 | 1 | 1 | 1 | 1
editor | 1 | 1 | 1 | 1 | 1 | 1
design | 1 | 1 | 1 | 1 | 1 | 1

## time.estimates
project | research | drafting | editing | design | print | launch-events
O | -10 | -10 | -10 | -10 | -10 | 10
N | -10 | -10 | -10 | -10 | -10 | 10
E | -10 | -10 | -10 | -10 | -10 | 10
V | -10 | -10 | -10 | -10 | -10 | 10
W | -10 | -10 | -10 | -10 | -10 | 10
K | -10 | -10 | -10 | -10 | -10 | 10
T | -10 | -10 | -10 | -10 | -10 | 10
D | -10 | -10 | -10 | -10 | -10 | 10
Z | -10 | -10 | -10 | -10 | -10 | 10
A | -10 | -10 | -10 | -10 | -10 | 10

## project.teams
project | role | staff | assigned_capacity
O | lead | Cornejo, Cierra | 0.5
O | researcher | unassigned | 1
O | editor | Cornejo, Cierra | 0.75
O | design | unassigned | 0.5
N | lead | Jones, Josiah | 1
N | researcher | Boon, Kevin | 1
N | editor | Boon, Kevin | 0.25
N | design | Proano Rodriguez, Leopoldo | 1
E | lead | Proano Rodriguez, Leopoldo | 0.75
E | researcher | Jones, Josiah | 0.25
E | editor | Compton, Ebony | 0.5
E | design | Proano Rodriguez, Leopoldo | 0.5
V | lead | Boon, Kevin | 0.75
V | researcher | unassigned | 1
V | editor | Proano Rodriguez, Leopoldo | 1
V | design | Boon, Kevin | 1
W | lead | Boon, Kevin | 0.5
W | researcher | Compton, Ebony | 0.5
W | editor | Cornejo, Cierra | 1
W | design | Proano Rodriguez, Leopoldo | 1
K | lead | Boon, Kevin | 1
K | researcher | Compton, Ebony | 0.75
K | editor | Cornejo, Cierra | 1
K | design | unassigned | 0.5
T | lead | Boon, Kevin | 0.5
T | researcher | Cornejo, Cierra | 0.75
T | editor | Jones, Josiah | 0.75
T | design | unassigned | 0.25
D | lead | unassigned | 0.25
D | researcher | Compton, Ebony | 0.75
D | editor | Proano Rodriguez, Leopoldo | 0.25
D | design | Jones, Josiah | 0.5
Z | lead | Compton, Ebony | 0.75
Z | researcher | Cornejo, Cierra | 0.25
Z | editor | Jones, Josiah | 0.5
Z | design | unassigned | 0.5
A | lead | Boon, Kevin | 0.25
A | researcher | Cornejo, Cierra | 0.75
A | editor | Proano Rodriguez, Leopoldo | 0.5
A | design | Compton, Ebony | 0.25