## resources
staff | capacity
Shelby | 40
Luis | 60
Taishawn | 100
Samantha | 100
Taylor | 100

## projects
project | probability | start | end
B | 100 | 2019-05-17 | 2019-06-16
A | 50 | 2019-07-25 | 2019-09-03
C | 100 | 2019-09-27 | 2019-10-27

## phases
x
research
drafting
editing
design
print
events

## roles
x
lead
researcher
editor
design

## responsibilities
role | research | drafting | editing | design | print | events
lead | 1 | 1 | 1 | 1 | 1 | 1
researcher | 1 | 1 | 1 | 0 | 0 | 0
editor | 0 | 0 | 1 | 0 | 0 | 0
design | 0 | 0 | 0 | 1 | 1 | 0

## time_estimates
project | research | drafting | editing | design | print | events
B | -40 | -10 | -10 | -10 | -10 | 10
A | -10 | -10 | -10 | 0 | 0 | 0
C | 0 | 0 | 0 | -10 | -10 | 10

## project_teams
project | role | staff | assigned_capacity
B | lead | Shelby | 25
A | lead | Taishawn | 100
C | lead | Luis | 100
B | researcher | Samantha | 100
A | researcher | Shelby | 75
C | researcher | Taishawn | 25
B | editor | Taylor | 100
A | editor | Shelby | 75
C | editor | Samantha | 25
B | design | Taishawn | 100
A | design | Shelby | 75
C | design | Luis | 100