## staff
id_staff | staff_name | staff_capacity | joined | departed
1 | Shelby | 40
2 | Luis | 60
3 | Taishawn | 100
4 | Samantha | 100
5 | Taylor | 100
6 | unassigned | 0

## projects
id_project | project_name | project_confirmed | project_start | project_end
1 | A | 0 | 2019-01-25 | 2019-06-03
2 | B | 1 | 2019-05-17 | 2019-06-16
3 | C | 1 | 2019-06-27 | 2019-09-27

## project_phases
id_project_phase | project_phase_name
1 | research
2 | drafting
3 | editing
4 | design
5 | print
6 | events

## out_of_office
id_out_of_office | staff_name | out_of_office_start | out_of_office_end | work_related
1 | Luis | 2019-07-23 | 2019-08-12 | 1
2 | Samantha | 2019-05-16 | 2019-06-10 | 0

## public_holidays
id_public_holidays | date | holiday_name
1 | 2019-01-01 | New Year's Day
2 | 2019-01-28 | Australia Day
3 | 2019-04-19 | Good Friday
4 | 2019-04-20 | Saturday before Easter Sunday
5 | 2019-04-21 | Easter Sunday
6 | 2019-04-22 | Easter Monday
7 | 2019-04-25 | Anzac Day
8 | 2019-06-10 | Queen's Birthday
9 | 2019-08-05 | Bank Holiday
10 | 2019-10-07 | Labour Day
11 | 2019-12-25 | Christmas Day
12 | 2019-12-26 | Boxing Day

## time_estimates
project_name | project_start | project_end | project_confirmed | research | drafting | editing | design | print | events
A | 2019-01-25 | 2019-06-03 | 0 | -10 | -10 | -10 | -10 | -10 | 10
B | 2019-05-17 | 2019-06-16 | 1 | -10 | -10 | -10 | -10 | -10 | 10
C | 2019-06-27 | 2019-09-27 | 1 | -10 | -10 | -10 | -10 | -10 | 10

## project_assignments
project_name | staff_name | staff_capacity | research | drafting | editing | design | print | events
A | Luis | 60 | 100 | 75 | 0 | 100 | 50 | 25
A | Samantha | 100 | 50 | 0 | 25 | 100 | 75 | 50
A | Shelby | 40 | 25 | 25 | 25 | 75 | 75 | 100
A | Taishawn | 100 | 25 | 75 | 50 | 25 | 50 | 25
A | Taylor | 100 | 25 | 75 | 75 | 100 | 50 | 50
A | unassigned | 0 | 50 | 100 | 25 | 75 | 0 | 25
B | Luis | 60 | 100 | 50 | 25 | 100 | 25 | 0
B | Samantha | 100 | 50 | 25 | 100 | 75 | 0 | 75
B | Shelby | 40 | 0 | 50 | 50 | 50 | 75 | 0
B | Taishawn | 100 | 25 | 25 | 50 | 75 | 25 | 75
B | Taylor | 100 | 0 | 25 | 75 | 75 | 75 | 75
B | unassigned | 0 | 0 | 25 | 50 | 75 | 50 | 50
C | Luis | 60 | 25 | 0 | 100 | 25 | 25 | 25
C | Samantha | 100 | 50 | 25 | 50 | 75 | 0 | 0
C | Shelby | 40 | 100 | 50 | 100 | 75 | 75 | 50
C | Taishawn | 100 | 75 | 50 | 50 | 25 | 25 | 50
C | Taylor | 100 | 75 | 25 | 100 | 75 | 0 | 50
C | unassigned | 0 | 100 | 0 | 25 | 75 | 100 | 25

## calendar
id_calendar | date
1 | 2018-12-26
2 | 2018-12-27
3 | 2018-12-28
4 | 2018-12-31
5 | 2019-01-01
6 | 2019-01-02
7 | 2019-01-03
8 | 2019-01-04
9 | 2019-01-07
10 | 2019-01-08
11 | 2019-01-09
12 | 2019-01-10
13 | 2019-01-11
14 | 2019-01-14
15 | 2019-01-15
16 | 2019-01-16
17 | 2019-01-17
18 | 2019-01-18
19 | 2019-01-21
20 | 2019-01-22
21 | 2019-01-23
22 | 2019-01-24
23 | 2019-01-25
24 | 2019-01-28
25 | 2019-01-29
26 | 2019-01-30
27 | 2019-01-31
28 | 2019-02-01
29 | 2019-02-04
30 | 2019-02-05
31 | 2019-02-06
32 | 2019-02-07
33 | 2019-02-08
34 | 2019-02-11
35 | 2019-02-12
36 | 2019-02-13
37 | 2019-02-14
38 | 2019-02-15
39 | 2019-02-18
40 | 2019-02-19
41 | 2019-02-20
42 | 2019-02-21
43 | 2019-02-22
44 | 2019-02-25
45 | 2019-02-26
46 | 2019-02-27
47 | 2019-02-28
48 | 2019-03-01
49 | 2019-03-04
50 | 2019-03-05
51 | 2019-03-06
52 | 2019-03-07
53 | 2019-03-08
54 | 2019-03-11
55 | 2019-03-12
56 | 2019-03-13
57 | 2019-03-14
58 | 2019-03-15
59 | 2019-03-18
60 | 2019-03-19
61 | 2019-03-20
62 | 2019-03-21
63 | 2019-03-22
64 | 2019-03-25
65 | 2019-03-26
66 | 2019-03-27
67 | 2019-03-28
68 | 2019-03-29
69 | 2019-04-01
70 | 2019-04-02
71 | 2019-04-03
72 | 2019-04-04
73 | 2019-04-05
74 | 2019-04-08
75 | 2019-04-09
76 | 2019-04-10
77 | 2019-04-11
78 | 2019-04-12
79 | 2019-04-15
80 | 2019-04-16
81 | 2019-04-17
82 | 2019-04-18
83 | 2019-04-19
84 | 2019-04-22
85 | 2019-04-23
86 | 2019-04-24
87 | 2019-04-25
88 | 2019-04-26
89 | 2019-04-29
90 | 2019-04-30
91 | 2019-05-01
92 | 2019-05-02
93 | 2019-05-03
94 | 2019-05-06
95 | 2019-05-07
96 | 2019-05-08
97 | 2019-05-09
98 | 2019-05-10
99 | 2019-05-13
100 | 2019-05-14
101 | 2019-05-15
102 | 2019-05-16
103 | 2019-05-17
104 | 2019-05-20
105 | 2019-05-21
106 | 2019-05-22
107 | 2019-05-23
108 | 2019-05-24
109 | 2019-05-27
110 | 2019-05-28
111 | 2019-05-29
112 | 2019-05-30
113 | 2019-05-31
114 | 2019-06-03
115 | 2019-06-04
116 | 2019-06-05
117 | 2019-06-06
118 | 2019-06-07
119 | 2019-06-10
120 | 2019-06-11
121 | 2019-06-12
122 | 2019-06-13
123 | 2019-06-14
124 | 2019-06-17
125 | 2019-06-18
126 | 2019-06-19
127 | 2019-06-20
128 | 2019-06-21
129 | 2019-06-24
130 | 2019-06-25
131 | 2019-06-26
132 | 2019-06-27
133 | 2019-06-28
134 | 2019-07-01
135 | 2019-07-02
136 | 2019-07-03
137 | 2019-07-04
138 | 2019-07-05
139 | 2019-07-08
140 | 2019-07-09
141 | 2019-07-10
142 | 2019-07-11
143 | 2019-07-12
144 | 2019-07-15
145 | 2019-07-16
146 | 2019-07-17
147 | 2019-07-18
148 | 2019-07-19
149 | 2019-07-22
150 | 2019-07-23
151 | 2019-07-24
152 | 2019-07-25
153 | 2019-07-26